## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Jhargram Mechanical Division | JHARGRAM | Sankrail | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME | SM/10289 | TSM/009474 |  | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer | JE (M) | 25/02/2022 | 03/03/2022 |  | 12/06/2023 | 3 | 0 | inf | inf | 100 | 41
2 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Alampur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/16978 | TSM/019800 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
3 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Balibandh w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/16995 | TSM/019757 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
4 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Parihati w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/16996 | TSM/019740 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
5 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Belda w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/16997 | TSM/019735 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
6 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Kapgari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/16998 | TSM/019744 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
7 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Tentulia w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17001 | TSM/019731 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
8 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Belia w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17002 | TSM/019723 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
9 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Khamarpara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17006 | TSM/019727 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
10 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Tiakitpur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17007 | TSM/019660 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
11 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Noharia w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17009 | TSM/019690 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
12 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bahirgram w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17010 | TSM/019719 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
13 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chandabila w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17013 | TSM/019712 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
14 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dahamunda w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17014 | TSM/019709 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
15 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Uttar Barashol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17015 | TSM/019710 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
16 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chichira w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17016 | TSM/019754 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
17 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gidhni w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17017 | TSM/019750 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
18 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Domahani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17018 | TSM/019716 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
19 | Jhargram Mechanical Division | JHARGRAM | Jamboni | DPR purpose for Design, development, supply and installation of smart water supply measurement & Monitoring system of Kapgari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17019 | TSM/019747 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
20 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Sonarimara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17020 | TSM/019707 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
21 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Jirapara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17021 | TSM/019706 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
22 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Sasrah w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17022 | TSM/019802 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
23 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chatinasole w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17023 | TSM/019801 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
24 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gopiballavpur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17038 | TSM/019803 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
25 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bhila w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17040 | TSM/019698 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
26 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Mahisa mura w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17043 | TSM/019693 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
27 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Barasol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17045 | TSM/019641 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
28 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Palashbani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17046 | TSM/019703 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
29 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Kankridahi w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17047 | TSM/019650 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
30 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chhahazari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17049 | TSM/019688 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
31 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Ghora Pincha w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17055 | TSM/019657 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
32 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Pitanow w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17061 | TSM/019702 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
33 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Mahulbani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17063 | TSM/019681 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
34 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Murakati w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17065 | TSM/019680 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
35 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Parashuli w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17067 | TSM/019699 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
36 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Sumitrapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17070 | TSM/019667 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
37 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bhalukasol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17072 | TSM/019675 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
38 | Jhargram Mechanical Division | JHARGRAM | Jamboni | Design, development, supply and installation of smart water supply measurement & Monitoring system of Susni w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17074 | TSM/019673 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
39 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Upar Baghuasol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17075 | TSM/019669 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 16/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
40 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chorchita w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17390 | TSM/019748 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
41 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gobindapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17391 | TSM/019742 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
42 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chingra w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17392 | TSM/019743 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
43 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Mahapal w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17393 | TSM/019745 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
44 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Shona Konia w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17394 | TSM/019733 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
45 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Junsola w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17397 | TSM/019724 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
46 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Petbindhi w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17399 | TSM/019729 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
47 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gohalmara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17400 | TSM/019715 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
48 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Pithapura w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17401 | TSM/019711 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
49 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of KENDANA w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17402 | TSM/019738 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
50 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Tentulia w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17403 | TSM/019718 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
51 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Naupara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17404 | TSM/019755 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
52 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Beliabera w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17405 | TSM/019761 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
53 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Rantua w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17406 | TSM/019764 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
54 | Jhargram Mechanical Division | JHARGRAM | Gopiballavpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Junsola w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17410 | TSM/019758 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 15/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
55 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chenchur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17431 | TSM/019796 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
56 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Murabani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17442 | TSM/019795 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
57 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Metial w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17534 | TSM/019792 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
58 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Khas Jangal w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17535 | TSM/019793 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
59 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dahatmal w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17536 | TSM/019791 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
60 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Rautarapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17537 | TSM/019790 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
61 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Brahmandana w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17538 | TSM/019788 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
62 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Darukuli w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17539 | TSM/019789 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
63 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Uransaol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17540 | TSM/019787 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
64 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bagmuri w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17541 | TSM/019784 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
65 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Rajband w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17542 | TSM/019781 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
66 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Panchami w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17543 | TSM/019780 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
67 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Burimol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17544 | TSM/019779 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
68 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Ramchandrapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17545 | TSM/019778 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
69 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bhaudi w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17546 | TSM/019777 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
70 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Lohameleya w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17547 | TSM/019767 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
71 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chakkua w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17548 | TSM/019762 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
72 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dudkundi w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17549 | TSM/019775 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
73 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Radhanagar w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17550 | TSM/019774 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
74 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gramohan w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17551 | TSM/019776 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
75 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Mantipa w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17552 | TSM/019739 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
76 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Amlachati w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17553 | TSM/019734 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
77 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Patharnala w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17554 | TSM/019725 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
78 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Champasol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17555 | TSM/019720 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
79 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dalkati w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17556 | TSM/019730 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
80 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Pukuria w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17557 | TSM/019756 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
81 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Chandri w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17563 | TSM/019794 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
82 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Simli w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17564 | TSM/019786 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
83 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Barabari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17576 | TSM/019798 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 18/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
84 | Jhargram Mechanical Division | JHARGRAM | Jhargram | Design, development, supply and installation of smart water supply measurement & Monitoring system of Pindrakuli w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17709 | TSM/019797 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
85 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Jhitka w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17943 | TSM/019647 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
86 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dahijuri w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17947 | TSM/019623 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
87 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dhamro w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17952 | TSM/019627 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
88 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Harda w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17955 | TSM/019639 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
89 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Birkarner w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17957 | TSM/019622 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
90 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Lalgarh w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17960 | TSM/019683 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
91 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Thakurpara w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17961 | TSM/019721 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
92 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Khasjangle w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17963 | TSM/019672 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
93 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Tilabani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17969 | TSM/019728 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
94 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Kantapahari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17970 | TSM/019652 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
95 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Netai w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17972 | TSM/019704 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
96 | Jhargram Mechanical Division | JHARGRAM | Binpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Kechenda w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17973 | TSM/019737 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
97 | Jhargram Mechanical Division | JHARGRAM | Binpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Banspahari w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17974 | TSM/019732 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
98 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Shaluka w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17975 | TSM/019713 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
99 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Sijua w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17976 | TSM/019714 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
100 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Ramgarh w/s scheme, Zone-I & II in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17977 | TSM/019708 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
101 | Jhargram Mechanical Division | JHARGRAM | Binpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Silda w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17979 | TSM/019746 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
102 | Jhargram Mechanical Division | JHARGRAM | Binpur - II | Design, development, supply and installation of smart water supply measurement & Monitoring system of Simulpal w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17980 | TSM/019751 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
103 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Simladanga w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17983 | TSM/019717 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
104 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Rohini w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17984 | TSM/019765 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
105 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Laudaha w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17985 | TSM/019763 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
106 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Ragra w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17986 | TSM/019773 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
107 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Kultikri w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17987 | TSM/019768 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
108 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Ankro w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17988 | TSM/019609 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
109 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Rampura w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17990 | TSM/019611 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
110 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Balishira w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17991 | TSM/019613 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
111 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bandarbani w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17992 | TSM/019616 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
112 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Raghunathpur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17993 | TSM/019705 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
113 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bankati w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17994 | TSM/019619 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
114 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Jakua w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17995 | TSM/019626 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
115 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Haripurbirua w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17997 | TSM/019628 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
116 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gobindapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17998 | TSM/019635 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 | 05/03/2024 |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
117 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Nepura w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/17999 | TSM/019696 | IOT | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
118 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Noagoan w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18004 | TSM/019634 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
119 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Gobindapur w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18005 | TSM/019633 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
120 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Satkuli Charar w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18016 | TSM/019638 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
121 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bakra w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18018 | TSM/019645 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
122 | Jhargram Mechanical Division | JHARGRAM | Binpur - I | Design, development, supply and installation of smart water supply measurement & Monitoring system of Jangalkhas w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18019 | TSM/019642 | IOT | Midnapur Mechanical (Drill.) Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
123 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Bhaman Sankrail w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18021 | TSM/019666 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
124 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Dumri-Nakrasuli w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18023 | TSM/019654 | IOT | Jhargram Mechanical Division | Assistant Engineer |  | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
125 | Jhargram Mechanical Division | JHARGRAM | Sankrail | Design, development, supply and installation of smart water supply measurement & Monitoring system of Karkatasol w/s scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | SM/18029 | TSM/019649 | IOT | Jhargram Mechanical Division | Assistant Engineer | JE (M) | 17/03/2023 |  |  | 05/05/2023 | 0 | 0 | inf | nan | 0 | 0
126 | Jhargram Mechanical Division | JHARGRAM |  | Supply, delivery of Computer and other allied accessories (through GeM portal) for Office of the Executive Engineer, Jhargram Mechanical Division, PHE Dte. in the district of Jhargram | SM/18717 | TSM/017884 | Support |  |  |  | 10/08/2023 |  |  | 10/08/2023 | 1 | 0 | inf | inf | 0 | 16
Total | [14 empty] | 4 | 0 | 0 | 0 |  | NAN