## Work Order Tracking (Rs. in Lak
Work Order Tracking (Rs. in Lakh)
SL. No. | Division | Scheme | Scheme Sm Code | Sanctioned Cost | No. of Work Orders | Work Value | Payment
1 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Ghusuru Piped water Supply Scheme at Naxalbari Block | SM/07423 | 38.97 | 1 | 36.04 | 34.48
2 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Matidhar Bijmillini T.E and Pathoria Habitation of Paschim Madati Piped water Supply Scheme (Part - A) | SM/07031 | 85.56 | 1 | 25.14 | 39.36
3 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for kantivita,Dhamnagach, & Purba bansgaon kismath villages under Bandargachh Piped water Supply Scheme | SM/07220 | 77.54 | 0 | 0 | 0
4 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme | SM/07033 | 75.17 | 4 | 41.04 | 47.32
5 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme | SM/07034 | 64.86 | 1 | 4.42 | 9.53
6 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Khopalasi village of Panchkolguri Piped water Supply Scheme | SM/07039 | 78 | 0 | 0 | 0
7 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for mahipal and Bandargachh village of Bandargachh Piped water Supply Scheme | SM/07042 | 81.93 | 1 | 0.98 | 18.35
8 | Darjeeling Division | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | 170.07 | 4 | 161.42 | 0
9 | Darjeeling Division | RIMBICK WATER SUPPLY SCHEME | SM/09427 | 627.68 | 4 | 628.93 | 516.27
10 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta | SM/10768 | 25.05 | 2 | 42.3 | 16.22
11 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Kolbong | SM/10834 | 104.23 | 8 | 144.48 | 75.99
12 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 | 218.24 | 5 | 206.65 | 151.13
13 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal jeewan Mission/Jal swapno Mission for balance household at Fatingtar | SM/11384 | 27.28 | 1 | 25.37 | 2.5
14 | Neorakhola W/S Mnt. Division | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | SM/11387 | 31.49 | 4 | 31.25 | 14.83
15 | Neorakhola W/S Mnt. Division | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | SM/11399 | 562.88 | 2 | 356.95 | 0
16 | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/11773 | 449.92 | 7 | 443.37 | 8.09
17 | Neorakhola W/S Mnt. Division | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | SM/10807 | 103.62 | 3 | 64.48 | 51.29
18 | Neorakhola W/S Mnt. Division | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 | 228.59 | 3 | 129.97 | 22.09
19 | Neorakhola W/S Mnt. Division | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II | SM/10822 | 19.74 | 2 | 16.77 | 5.84
20 | Neorakhola W/S Mnt. Division | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | 299.8 | 6 | 192.22 | 51.18
21 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | SM/11315 | 21.28 | 2 | 20.51 | 7.94
22 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Krishi kunj | SM/11308 | 5.7 | 1 | 5.48 | 2.57
23 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme | SM/07038 | 89.15 | 3 | 39.15 | 24.3
24 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme | SM/07218 | 98.75 | 4 | 71.12 | 88.14
25 | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 87 Nos of School under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong. | SM/11355 | 0 | 1 | 232.24 | 74.95
26 | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme | SM/13427 | 244.41 | 6 | 203.23 | 173.61
27 | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme | SM/13428 | 267.54 | 7 | 231.06 | 49.87
28 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14530 | 1651.09 | 2 | 1587.3 | 0
29 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 | 1462.38 | 4 | 1377.75 | 1017.01
30 | Neorakhola W/S Mnt. Division | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | SM/15909 | 304.67 | 2 | 279.12 | 109.65
31 | Neorakhola W/S Mnt. Division | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme | SM/16384 | 557.87 | 3 | 535.5 | 222.84
32 | Neorakhola W/S Mnt. Division | BARA MUNGWA PIPED WATER SUPPLY SCHEME | SM/15893 | 476.33 | 3 | 470 | 0
33 | Neorakhola W/S Mnt. Division | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 | 752.32 | 5 | 750.14 | 302.12
34 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) | SM/15649 | 611 | 1 | 605.39 | 0
35 | Neorakhola W/S Mnt. Division | SINGALILA FOREST PWSS | SM/16771 | 398.31 | 3 | 365.83 | 121.76
36 | Neorakhola W/S Mnt. Division | PWS Scheme for Sepoy Dhura Tea Garden | SM/15651 | 525.04 | 3 | 446.79 | 0
37 | Neorakhola W/S Mnt. Division | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15655 | 743.37 | 3 | 733.47 | 423.51
38 | Neorakhola W/S Mnt. Division | RELLING PIPED WATER SUPPLY SCHEME. | SM/15879 | 937.57 | 3 | 901.47 | 152.39
39 | Neorakhola W/S Mnt. Division | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS | SM/17191 | 879.54 | 1 | 230.27 | 0
40 | Neorakhola W/S Mnt. Division | LEBONG & MINERAL TEA GARDEN PWSS | SM/18726 | 1123.93 | 3 | 1103.38 | 75
41 | Kurseong Division | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | 1470.02 | 3 | 1353.52 | 571.95
42 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA | SM/11337 | 14.29 | 2 | 12.31 | 3.64
43 | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. | SM/18784 | 623.79 | 7 | 579.18 | 133
44 | Kurseong Division | Piped Water supply scheme of Ambotia T.E., Saint Mary's - I, Spring side, Makaibari and Karbia T.E. by pumping water from Balasan river under PHED Kurseong Division, GTA | null | 0 | 0 | 0 | 0
45 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Mangalsing Piped water Supply Scheme | SM/07029 | 56.89 | 1 | 3.73 | 48.74
46 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme | SM/07216 | 61.95 | 6 | 31.41 | 23.11
47 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Rajajhar & Rangapani village of Ranidanga-Rangapani Piped water Supply Scheme | SM/07037 | 76.12 | 2 | 2.72 | 2.24
48 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme | SM/07045 | 92.52 | 2 | 68.6 | 31.86
49 | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] | SM/10262 | 159.17 | 12 | 123.59 | 75.9
50 | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 | 244.94 | 9 | 252.93 | 146.39
51 | Neorakhola W/S Mnt. Division | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 | 101.18 | 2 | 93.64 | 36.34
52 | Neorakhola W/S Mnt. Division | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | SM/11378 | 40.64 | 3 | 36.64 | 8.06
53 | Neorakhola W/S Mnt. Division | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 | 1129.94 | 4 | 1041.24 | 527.95
54 | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME | SM/11777 | 164.44 | 5 | 111.23 | 5.98
55 | Neorakhola W/S Mnt. Division | Creation of gravity based provision of drinking water from spring water source of anganwadi(119 nos) centers under Darjeeling pulbazar block in the district of Darjeeling under Neorakhola water supply & maintenance division, P.H.E. Directorate | SM/10796 | 0 | 1 | 334.99 | 316.04
56 | Neorakhola W/S Mnt. Division | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | SM/10798 | 226.19 | 2 | 118.28 | 0
57 | Neorakhola W/S Mnt. Division | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | SM/10803 | 91.97 | 3 | 61.51 | 22.6
58 | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | SM/10825 | 118.57 | 3 | 93.41 | 35.7
59 | Neorakhola W/S Mnt. Division | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 | 150.71 | 4 | 177.82 | 20.09
60 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis | SM/11322 | 14.74 | 2 | 13.04 | 0
61 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA | SM/11330 | 13.49 | 2 | 12.44 | 6.41
62 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. | SM/11300 | 20.83 | 2 | 19.29 | 0
63 | Neorakhola W/S Mnt. Division | Providing Functional households Tap connection under JSP Programme for PWS Scheme Soureni Bazar | SM/11306 | 23.6 | 1 | 22.21 | 6.63
64 | Neorakhola W/S Mnt. Division | Providing functional household Tap connection under JSP Programme for PWS Scheme Manju Dara Gaon | SM/11307 | 6.09 | 1 | 5.33 | 2.07
65 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11331 | 31.31 | 2 | 28.31 | 10.06
66 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singtam Tea Garden | SM/11338 | 176.87 | 2 | 176.08 | 0
67 | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11943 | 212.19 | 3 | 210.48 | 134.09
68 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | SM/11890 | 760.91 | 3 | 754.83 | 655.64
69 | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME | SM/12807 | 649.84 | 10 | 541.93 | 16.66
70 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/11891 | 865.61 | 3 | 860.97 | 726.03
71 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11347 | 39.89 | 2 | 38.8 | 16.19
72 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11349 | 79.79 | 2 | 78.19 | 0
73 | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME | SM/12038 | 119.17 | 4 | 66.28 | 33.16
74 | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme | SM/13433 | 587.76 | 9 | 473.21 | 87.82
75 | Siliguri W/S Division | Khoklong Piped Water Supply Scheme | SM/13437 | 187.01 | 10 | 168.16 | 19.47
76 | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme | SM/13395 | 271.14 | 8 | 232.27 | 39.2
77 | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) | SM/14150 | 1709.08 | 13 | 1316.24 | 60.22
78 | Neorakhola W/S Mnt. Division | KOLBONG KHASMAHAL PWSS | SM/15840 | 214.49 | 2 | 213.09 | 99.78
79 | Neorakhola W/S Mnt. Division | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | SM/15882 | 423.41 | 2 | 418.07 | 56.82
80 | Neorakhola W/S Mnt. Division | MAJUA PIPED WATER SUPPLY SCHEME. | SM/15874 | 301.04 | 3 | 284.76 | 63.75
81 | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME | SM/15925 | 610.74 | 9 | 542.23 | 14.96
82 | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME | SM/15928 | 368.86 | 9 | 346.01 | 8.42
83 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BAIRAGI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15855 | 0 | 1 | 6.26 | 0
84 | Neorakhola W/S Mnt. Division | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 | 496.03 | 4 | 225.67 | 0
85 | Neorakhola W/S Mnt. Division | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 | 560.14 | 4 | 530.53 | 327.7
86 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15860 | 0 | 1 | 6.26 | 0
87 | Neorakhola W/S Mnt. Division | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 | 335.44 | 4 | 331.25 | 74.11
88 | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) | SM/15929 | 741.26 | 8 | 598.9 | 60.5
89 | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) | SM/18321 | 1713.48 | 12 | 1291.22 | 18.16
90 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11348 | 27.68 | 2 | 25.15 | 2.5
91 | Kurseong Division | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | SM/18638 | 1513.58 | 3 | 1344.48 | 174.83
92 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 | 1246.59 | 4 | 1127.64 | 624.88
93 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra | SM/10561 | 16.73 | 2 | 13.71 | 4.66
94 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14147 | 1120.63 | 3 | 1106.08 | 601.99
95 | Neorakhola W/S Mnt. Division | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/18821 | 1262.02 | 2 | 1224.28 | 0
96 | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-II PWSS | SM/18659 | 8823.99 | 2 | 30.87 | 4.2
97 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18601 | 2696.35 | 2 | 2574.55 | 1425
98 | Kurseong Division | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18878 | 199.02 | 0 | 0 | 0
99 | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-III PWSS | SM/18792 | 7379.87 | 2 | 6754.66 | 0
100 | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12749 | 335.45 | 7 | 262.42 | 104.3
101 | Kurseong Division | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | 3828.95 | 4 | 3619 | 1302.2
102 | Kurseong Division | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | 1203.19 | 4 | 1173.41 | 2.35
103 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15854 | 0 | 1 | 6.26 | 2.82
104 | Darjeeling Division | BHIRGAON DHARGAON PWSS | SM/18714 | 162.75 | 1 | 152.77 | 0
105 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Khudiram Pally-I, khudiram Pally-II, Rail cly & Sree Colony Habitation of Dumriguri Piped W/S Supply Scheme ( Part-B ) at Naxalbari Block | SM/07427 | 82.41 | 0 | 0 | 68.28
106 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block | SM/07428 | 77.59 | 3 | 16.83 | 54.48
107 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Pelku (JL No-71) & Thiknikata (JL No.-74) Mouzas of Kawakhali Pipe water Supply Scheme | SM/07213 | 99.9 | 1 | 74.02 | 0
108 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Dhakpara village of Budharugaon Piped water Supply Scheme | SM/07214 | 55.85 | 0 | 0 | 0
109 | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal Swpna Programme for Samar Nagar& Debidanga area of Kalkut Mouza, Uttar Palash and Dakshin Palash area of Palash Mouza and Kalabari Mouza ( Part ) of Kalkut Piped W/S Scheme at | SM/08296 | 63.28 | 1 | 19.62 | 52.86
110 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth | SM/10766 | 7.21 | 2 | 5.83 | 2.02
111 | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village | SM/10770 | 21.64 | 2 | 16.98 | 4.93
112 | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND | SM/10470 | 701.4 | 2 | 600.31 | 399.38
113 | Darjeeling Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] | SM/10258 | 112.63 | 5 | 72.46 | 72.46
114 | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | SM/10789 | 100.65 | 3 | 146.99 | 17.66
115 | Neorakhola W/S Mnt. Division | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. | SM/10790 | 100.33 | 2 | 1.9 | 47.75
116 | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME | SM/10025 | 1506.6 | 22 | 1484.9 | 511.47
117 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam | SM/11393 | 184.74 | 2 | 174.64 | 0
118 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | SM/11394 | 199.28 | 3 | 184.59 | 47.34
119 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Lower Bish Acre, Ghayabari. | SM/11397 | 69.47 | 3 | 66.5 | 0
120 | Kurseong Division | CONSTRUCTION OF SOURCE AND OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SONADA TO ACCOMODATE TWO MOUZAS MAINLY SONADA FOREST & SONADA KHASMAHAL UNDER SUKHIA POKHARI BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, PHED. | SM/19039 | 2250.46 | 0 | 0 | 0
121 | Neorakhola W/S Mnt. Division | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 | 1242.31 | 4 | 1237.7 | 763.89
122 | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10477 | 335.48 | 10 | 282.01 | 107.77
123 | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME | SM/10476 | 807.68 | 9 | 718.25 | 54.01
124 | Neorakhola W/S Mnt. Division | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | SM/10805 | 123.11 | 2 | 79.07 | 34.79
125 | Neorakhola W/S Mnt. Division | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA | SM/10810 | 151.73 | 2 | 84.57 | 39.5
126 | Neorakhola W/S Mnt. Division | BARA CHENGA PIPED WATER SUPPLY SCHEME | SM/10816 | 422.1 | 7 | 395.43 | 100.32
127 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 | 98.99 | 4 | 84.94 | 63.03
128 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12179 | 663.63 | 2 | 636.4 | 445.36
129 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA | SM/11333 | 26.69 | 2 | 24.69 | 9.25
130 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 | 923.75 | 4 | 940.85 | 438.78
131 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12736 | 1292.66 | 3 | 1282.53 | 1049.72
132 | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 | 669.61 | 12 | 646.79 | 144.37
133 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/11952 | 884.34 | 3 | 884.41 | 634.84
134 | Neorakhola W/S Mnt. Division | PWS Scheme for Rohini Tea Garden | SM/11938 | 408.51 | 3 | 334.16 | 127.93
135 | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 | 629.15 | 10 | 584.18 | 73.41
136 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/13041 | 1164.09 | 3 | 1168.73 | 826.29
137 | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13957 | 451.2 | 2 | 391.94 | 53.44
138 | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13958 | 330.4 | 2 | 307.43 | 122.02
139 | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme | SM/13391 | 417.78 | 10 | 352.54 | 132.62
140 | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME | SM/13467 | 647.04 | 7 | 435.46 | 82.46
141 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/14529 | 2347.04 | 6 | 2063.47 | 1456.62
142 | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME | SM/15271 | 148.34 | 7 | 100.83 | 5.73
143 | Neorakhola W/S Mnt. Division | BLOOMFIELD TEA GARDEN PWSS | SM/15910 | 447.08 | 4 | 432.73 | 104.03
144 | Neorakhola W/S Mnt. Division | RIMBICK Piped Water Supply Scheme | SM/16123 | 716.55 | 3 | 715.88 | 0
145 | Neorakhola W/S Mnt. Division | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme | SM/16142 | 334.74 | 2 | 492.8 | 0
146 | Neorakhola W/S Mnt. Division | GOKE PIPED WATER SUPPLY SCHEME. | SM/15873 | 932.73 | 2 | 845.95 | 0
147 | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME | SM/15926 | 352.69 | 8 | 229.58 | 3.46
148 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DANGARVITA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15627 | 0 | 1 | 6.26 | 0
149 | Neorakhola W/S Mnt. Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 | 656.45 | 3 | 501.81 | 6.99
150 | Neorakhola W/S Mnt. Division | SUKNA PIPED WATER SUPPLY SCHEME | SM/15653 | 304.63 | 3 | 251.42 | 6.99
151 | Kurseong Division | PWS Scheme for Edenvale Tea Garden | SM/18710 | 150.23 | 2 | 136.43 | 49.77
152 | Kurseong Division | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/19033 | 1424.7 | 1 | 1230.38 | 0
153 | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme | SM/13438 | 184.33 | 9 | 171.83 | 51.91
154 | Kurseong Division | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 | 2936.38 | 2 | 2457.67 | 0
155 | Neorakhola W/S Mnt. Division | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | SM/18724 | 1783.75 | 2 | 1662.59 | 0
156 | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18386 | 1249.24 | 7 | 956.15 | 74.18
157 | Kurseong Division | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | 194.06 | 0 | 0 | 0
158 | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) | SM/07046 | 98.86 | 5 | 87.52 | 59.17
159 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme | SM/07217 | 80.78 | 4 | 95.49 | 69.42
160 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07040 | 85.15 | 1 | 37.26 | 35.86
161 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) | SM/07043 | 71.82 | 5 | 43.13 | 38.16
162 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u | SM/08295 | 85.65 | 2 | 1.62 | 43.46
163 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield | SM/10772 | 15.76 | 3 | 14.32 | 0
164 | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME | SM/10097 | 913.6 | 14 | 1132.83 | 412.67
165 | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME | SM/09830 | 566.48 | 22 | 585.79 | 320.36
166 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin | SM/09078 | 23.31 | 1 | 0.75 | 12.4
167 | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME | SM/10714 | 849.31 | 11 | 665.3 | 115.24
168 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 | 318.71 | 4 | 305.31 | 290.02
169 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | SM/11389 | 15.54 | 4 | 13.25 | 4.71
170 | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under Jal Jeewan Mission/ Jal Swapno Programme at New Fallodi Tea Garden ( Mandir Goan) | SM/11390 | 10.66 | 1 | 9.11 | 0
171 | Neorakhola W/S Mnt. Division | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/11395 | 306.47 | 2 | 268.66 | 0
172 | Neorakhola W/S Mnt. Division | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | SM/11396 | 234.66 | 2 | 168.86 | 43.2
173 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) | SM/10773 | 21.6 | 3 | 19.16 | 7.84
174 | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source of school (31 nos) under Mirik Block in the District of Darjeeling under Neorakhola water supply & Mtc Division, P.H.E Dte. | SM/10784 | 0 | 1 | 94.19 | 16.24
175 | Neorakhola W/S Mnt. Division | Nipania Piped water Supply Scheme. | SM/10815 | 461.01 | 4 | 411.7 | 241.39
176 | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 | 167.48 | 2 | 102.53 | 21.54
177 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. | SM/11318 | 7.31 | 2 | 6.36 | 2.69
178 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA | SM/11327 | 15.46 | 2 | 13.42 | 0
179 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11329 | 19.72 | 2 | 18.78 | 8.87
180 | Neorakhola W/S Mnt. Division | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon | SM/11304 | 23.72 | 2 | 20.39 | 10.67
181 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11334 | 33.35 | 2 | 28.17 | 0
182 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/11954 | 333.26 | 3 | 321.5 | 84.44
183 | Neorakhola W/S Mnt. Division | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | SM/12367 | 1786.06 | 2 | 1750.73 | 1287.6
184 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11346 | 21.35 | 2 | 20.32 | 0
185 | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME | SM/12037 | 125.17 | 4 | 81.17 | 45.26
186 | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate | SM/11360 | 0 | 1 | 310.44 | 202.42
187 | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | 0 | 6 | 23.59 | 0
188 | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/13571 | 1420.81 | 2 | 1373.22 | 842.46
189 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13959 | 228.01 | 3 | 215.16 | 0
190 | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 | 92.86 | 6 | 76.64 | 8.7
191 | Neorakhola W/S Mnt. Division | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16161 | 322.85 | 2 | 261.17 | 0
192 | Neorakhola W/S Mnt. Division | PANIGHATA Piped Water Supply Scheme | SM/16144 | 363.69 | 5 | 308.47 | 5.32
193 | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15927 | 455.46 | 7 | 427.23 | 1.2
194 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT OMI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15859 | 0 | 1 | 6.26 | 0
195 | Neorakhola W/S Mnt. Division | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) | SM/15892 | 161.01 | 3 | 158.22 | 2.13
196 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA BANSGAON PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15629 | 0 | 1 | 6.26 | 0
197 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15631 | 0 | 1 | 6.26 | 0
198 | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 | 890.47 | 10 | 789.58 | 126.86
199 | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME | SM/15924 | 858.49 | 13 | 712.24 | 167.93
200 | Neorakhola W/S Mnt. Division | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | SM/15877 | 150.95 | 3 | 133.5 | 34.11
201 | Neorakhola W/S Mnt. Division | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. | SM/15878 | 277.07 | 4 | 244.75 | 0
202 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/18634 | 1305.54 | 3 | 1194.6 | 120.74
203 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | SM/18635 | 1907.13 | 3 | 1835.85 | 303.32
204 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/18636 | 1046.24 | 1 | 1022.22 | 308.82
205 | Neorakhola W/S Mnt. Division | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10817 | 379.09 | 4 | 191.37 | 73.56
206 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | SM/11854 | 942.58 | 3 | 935.51 | 354.93
207 | Neorakhola W/S Mnt. Division | RONGCHONG AND LABDA PWSS | SM/18729 | 1302.23 | 2 | 1191.21 | 279.03
208 | Neorakhola W/S Mnt. Division | DARJEELING-PULBAZAR PUMPING-I PWSS | SM/18827 | 17368.24 | 2 | 15903.64 | 0
209 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme | SM/07030 | 93.81 | 3 | 68.77 | 58.38
210 | Neorakhola W/S Mnt. Division | DAWAIPANI & TUKDAH TEA GARDEN PWSS | SM/18752 | 1141.66 | 2 | 1000.97 | 50
211 | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME | SM/10724 | 1047.38 | 10 | 1015.19 | 246.35
212 | Kurseong Division | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME | SM/18879 | 93.17 | 0 | 0 | 0
213 | Siliguri W/S Division | IMPLEMENTATION OF AFFORDABLE IOT SYSTEM AT PURBA MADATI WATER SUPPLY SCHEME IN PHANSIDEWA BLOCK UNDER DARJEELING DISTRICT. | null | 0 | 0 | 0 | 0
214 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) | SM/07047 | 66.13 | 4 | 111.37 | 32.67
215 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan | SM/10769 | 22.77 | 2 | 18.78 | 11.39
216 | Neorakhola W/S Mnt. Division | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village | SM/10771 | 14.21 | 4 | 13.8 | 6.38
217 | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | SM/10774 | 18.12 | 3 | 17.26 | 0
218 | Darjeeling Division | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | 269.79 | 15 | 202.06 | 143.69
219 | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME | SM/10108 | 640.28 | 13 | 712.66 | 132
220 | Neorakhola W/S Mnt. Division | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | SM/10687 | 0 | 4 | 337.4 | 325.97
221 | Neorakhola W/S Mnt. Division | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | SM/10622 | 0 | 4 | 490.01 | 260.19
222 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna | SM/11380 | 10.66 | 2 | 9.39 | 3.78
223 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | SM/11383 | 65.26 | 3 | 57.33 | 32.63
224 | Neorakhola W/S Mnt. Division | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. | SM/11385 | 47.07 | 3 | 42.2 | 2
225 | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10785 | 0 | 3 | 11.86 | 9.01
226 | Neorakhola W/S Mnt. Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | SM/10799 | 80.89 | 1 | 47.25 | 21
227 | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | SM/10801 | 163.3 | 2 | 100.88 | 52.16
228 | Neorakhola W/S Mnt. Division | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA | SM/10804 | 123.59 | 2 | 72.78 | 30.98
229 | Neorakhola W/S Mnt. Division | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10809 | 115.19 | 2 | 67.61 | 0
230 | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA | SM/10828 | 117.73 | 3 | 80.72 | 36.78
231 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Thulung Gaon | SM/10830 | 78.67 | 2 | 76.53 | 16.61
232 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. | SM/11317 | 12.12 | 2 | 10.99 | 0
233 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. | SM/11320 | 19.74 | 2 | 17.94 | 6.16
234 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div | SM/11323 | 22.61 | 2 | 21.71 | 7.45
235 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III | SM/11301 | 8.63 | 2 | 7.83 | 4.32
236 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail | SM/11305 | 14.68 | 2 | 13.58 | 6.77
237 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Bada kothi | SM/11310 | 4.51 | 1 | 3.78 | 2.03
238 | Neorakhola W/S Mnt. Division | Augmentation of source for lower Takbia | SM/11374 | 28.05 | 2 | 24.72 | 9.87
239 | Neorakhola W/S Mnt. Division | Providing household tap connection from existing scheme at Museykhola & Dokan Dhura | SM/11818 | 50.5 | 1 | 46.23 | 0
240 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11352 | 32.24 | 1 | 31.04 | 0
241 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | SM/11353 | 72.84 | 2 | 64.04 | 0
242 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 | 990.4 | 4 | 993.32 | 760.21
243 | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source for 16 Numbers of Aganwadi Centers in Block- Kurseong, under the District of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte,. | SM/11362 | 0 | 1 | 37.03 | 11.94
244 | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | 0 | 7 | 22.62 | 3.19
245 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 | 1047.9 | 4 | 1018.82 | 815.24
246 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 | 1217.59 | 6 | 1218.78 | 300.06
247 | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME | SM/14834 | 111.08 | 5 | 112.84 | 18.32
248 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 | 517.62 | 2 | 485.43 | 0
249 | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13960 | 300.61 | 3 | 284.52 | 141.65
250 | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme | SM/13392 | 294.72 | 7 | 264.2 | 83.53
251 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14528 | 1138.22 | 3 | 1061.88 | 344.04
252 | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/14149 | 1893.19 | 4 | 1783.12 | 1015.99
253 | Siliguri W/S Division | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME | SM/15272 | 106.93 | 4 | 79.37 | 7.7
254 | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME | SM/15273 | 188.14 | 6 | 125.46 | 3.27
255 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DEBURAM PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15858 | 0 | 1 | 6.26 | 0
256 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16532 | 1658.37 | 3 | 1647.44 | 113.72
257 | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16533 | 1182.41 | 2 | 1149.25 | 485.23
258 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | SM/16535 | 1055.89 | 3 | 1051.2 | 648.09
259 | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/15908 | 758.56 | 9 | 631.16 | 15.64
260 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15630 | 0 | 1 | 6.26 | 0
261 | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME | SM/15648 | 230 | 3 | 177.03 | 7.64
262 | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME. | SM/15875 | 217.84 | 0 | 0 | 0
263 | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | 108.57 | 6 | 91.25 | 72.81
264 | Neorakhola W/S Mnt. Division | SITTONG KHASMAHAL PWSS | SM/18336 | 1082.47 | 1 | 921.25 | 0
265 | Kurseong Division | PWS Scheme for Mirik Khasmahal | SM/18650 | 1261.17 | 3 | 1245.13 | 136.14
266 | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | 1262.65 | 4 | 1156.01 | 570.67
267 | Kurseong Division | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/18880 | 197.84 | 0 | 0 | 0
268 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block | SM/07425 | 50.62 | 3 | 49.3 | 46.72
269 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block | SM/07426 | 57.56 | 3 | 36.39 | 45.7
270 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) | SM/07049 | 98.65 | 6 | 98.44 | 56.46
271 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Panchkolguri & Jhauguri village of Panchkolguri Piped water Supply Scheme | SM/07219 | 55.74 | 0 | 0 | 0
272 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ranidanga & Shaibhita village of Ranidanga-Rangapani Piped water Supply Scheme | SM/07036 | 79.26 | 0 | 0 | 1.82
273 | Neorakhola W/S Mnt. Division | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | SM/10765 | 18 | 3 | 18.59 | 0
274 | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. | SM/09828 | 613.39 | 21 | 631.66 | 280.69
275 | Darjeeling Division | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | SM/10261 | 34.5 | 3 | 19.62 | 5.7
276 | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | 39.28 | 6 | 50.75 | 19.82
277 | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME | SM/10107 | 641.16 | 17 | 738.97 | 482.44
278 | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal swapno programme for Mirjangla,Mirjnaglar Chhat, Birsing, Fakna Mouza of Birsing Piped W/S Scheme at Naxalbari Block under Siliguri Sub Division, P.H.E Dte. ( Phase-II ) | SM/09079 | 57.6 | 2 | 45.12 | 41.55
279 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay | SM/10780 | 17.18 | 2 | 16.83 | 6.92
280 | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME | SM/10183 | 1681.3 | 36 | 1660.6 | 885.19
281 | Neorakhola W/S Mnt. Division | Providing functional household tap connection existing PWSS at Bunkulung | SM/11391 | 33.5 | 1 | 27.91 | 0
282 | Neorakhola W/S Mnt. Division | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | SM/11392 | 180.91 | 3 | 162.31 | 0
283 | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 | 157.45 | 6 | 117.34 | 12.55
284 | Neorakhola W/S Mnt. Division | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA | SM/10800 | 143.69 | 2 | 86.92 | 0
285 | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | SM/10806 | 122.1 | 3 | 70.97 | 46.79
286 | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10808 | 189.33 | 2 | 110.43 | 38.82
287 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singbuli factory gaon | SM/10831 | 77.24 | 2 | 64.49 | 7.34
288 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 | 595.74 | 3 | 590.98 | 360.52
289 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. | SM/11314 | 10.67 | 2 | 10.05 | 0
290 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, | SM/11316 | 7.68 | 2 | 7.09 | 0
291 | Neorakhola W/S Mnt. Division | Singla Tea Garden water supply scheme. | SM/11339 | 384.26 | 3 | 289.52 | 186.52
292 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | SM/11855 | 408.25 | 2 | 372.52 | 198.16
293 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | SM/11856 | 290.75 | 2 | 239.86 | 30
294 | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME | SM/12750 | 754.32 | 11 | 694.1 | 23.98
295 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11345 | 24.77 | 2 | 23.93 | 0
296 | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme | SM/13429 | 347.93 | 7 | 271.09 | 133.43
297 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/13955 | 237.69 | 2 | 231.46 | 0
298 | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme | SM/13393 | 339.93 | 7 | 281.68 | 121.49
299 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 | 1660.67 | 5 | 1618.27 | 1068.31
300 | Neorakhola W/S Mnt. Division | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 | 268.11 | 2 | 240.56 | 0
301 | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME | SM/15270 | 148.87 | 6 | 109.53 | 33.4
302 | Neorakhola W/S Mnt. Division | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 | 142.59 | 3 | 35.28 | 12.52
303 | Kurseong Division | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | 327.7 | 2 | 305.2 | 49.17
304 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DAMDAMA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15857 | 0 | 1 | 6.26 | 0
305 | Neorakhola W/S Mnt. Division | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME | SM/15894 | 295.85 | 2 | 251.87 | 0
306 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15626 | 0 | 2 | 6.26 | 0
307 | Kurseong Division | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 | 210.61 | 2 | 201.76 | 0
308 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Budharugaon village of Budharugaon Piped water Supply Scheme | SM/07041 | 91.98 | 1 | 41.87 | 21.89
309 | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME | SM/09827 | 870.41 | 18 | 818.47 | 486.49
310 | Kurseong Division | PWS scheme for St. Mary's & Goethals | SM/15661 | 338.76 | 3 | 307.89 | 0
311 | Neorakhola W/S Mnt. Division | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/15876 | 790.03 | 3 | 755.02 | 385.69
312 | Neorakhola W/S Mnt. Division | BARBATIA KHASMAHAL PWSS | SM/18189 | 404.81 | 2 | 195.53 | 24.66
313 | Neorakhola W/S Mnt. Division | BADAMTAM TEA GARDEN PWSS | SM/18725 | 1124.76 | 3 | 1094.55 | 0
314 | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | SM/18727 | 1928.5 | 2 | 1938.1 | 0
315 | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME | SM/18385 | 2394.79 | 38 | 1635.96 | 261.95
316 | Neorakhola W/S Mnt. Division | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 | 230.73 | 3 | 215.95 | 0
317 | Darjeeling Division | Hatta Water Supply Scheme | SM/09449 | 313.13 | 4 | 314.28 | 271.97
318 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under JSP Programme for PWS scheme at Kataray forest Busty | SM/11302 | 9.52 | 1 | 7.66 | 4.76
319 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18822 | 3724.46 | 3 | 3448.97 | 489.84
320 | Kurseong Division | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | 3308.68 | 3 | 2589.56 | 5.67
321 | Kurseong Division | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | 1969.93 | 3 | 1531.77 | 275.86
322 | Kurseong Division | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 | 1208.42 | 3 | 1210.86 | 112.2
323 | Kurseong Division | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | SM/18648 | 2338.45 | 2 | 2171.44 | 0
324 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block | SM/07422 | 18.5 | 2 | 16.27 | 10.6
325 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) | SM/07032 | 31.72 | 5 | 40.18 | 11.52
326 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme | SM/07215 | 59.78 | 5 | 60.25 | 32.97
327 | Siliguri W/S Division | Extension of Piped Water Supply (PWS) to Anganwadi Centers (AWCs) located within the command area of PWSS under Siliguri W/S Division. | SM/07966 | 0 | 0 | 0 | 0
328 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme | SM/07035 | 62.07 | 3 | 69.3 | 46.42
329 | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme in 5 Habitation ( Ghaiter Busrty, Gurira Zote , Nagar Zote, NDDP Busty , Taluk Zote ) at Village Guria of | SM/09203 | 66.16 | 1 | 1.05 | 47.04
330 | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D | SM/09204 | 21.41 | 1 | 0.21 | 8.98
331 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village | SM/10764 | 21.15 | 2 | 20.72 | 7.86
332 | Darjeeling Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | 80.55 | 13 | 69.58 | 50.54
333 | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME | SM/10073 | 910.44 | 17 | 863.78 | 434.9
334 | Neorakhola W/S Mnt. Division | Piped water supply scheme for Daragoan Lekharga. | SM/10836 | 67.94 | 3 | 59.09 | 5
335 | Neorakhola W/S Mnt. Division | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | SM/11381 | 76.94 | 4 | 59.27 | 25
336 | Neorakhola W/S Mnt. Division | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | SM/11398 | 379.74 | 3 | 335.84 | 134.14
337 | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME | SM/11776 | 386.83 | 6 | 337.86 | 7.13
338 | Neorakhola W/S Mnt. Division | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | SM/10826 | 178.67 | 2 | 97.9 | 40.81
339 | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | SM/10827 | 213.75 | 2 | 126.58 | 25
340 | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING | SM/10824 | 542.09 | 2 | 599.19 | 114.21
341 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | SM/11321 | 17.13 | 2 | 13.56 | 8.57
342 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution networks retrofitting under JSP Programme for PWS Scheme for Chowandhura | SM/11311 | 11.81 | 1 | 11.04 | 0
343 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA | SM/11332 | 26.39 | 2 | 25.25 | 13.2
344 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA | SM/11336 | 13.82 | 2 | 11.49 | 3.64
345 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 | 319.88 | 4 | 306.38 | 212.34
346 | Neorakhola W/S Mnt. Division | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 | 2044.39 | 5 | 1774.37 | 1383.13
347 | Neorakhola W/S Mnt. Division | Augmentation of source and provding FHTC at Bijanbari Bazaar | SM/11375 | 42.06 | 1 | 35.85 | 20.73
348 | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME | SM/12034 | 197.56 | 5 | 163.97 | 9.59
349 | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 | 563.65 | 9 | 502.49 | 144.56
350 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11351 | 18.6 | 3 | 19.78 | 6.98
351 | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME | SM/11785 | 165.38 | 7 | 145.22 | 18.99
352 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 | 768.51 | 4 | 743.66 | 601.97
353 | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME | SM/14835 | 98.37 | 6 | 48.63 | 12.32
354 | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME | SM/14846 | 847.7 | 9 | 762.22 | 56.19
355 | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme | SM/13436 | 216.92 | 7 | 169.48 | 8.83
356 | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. | SM/14517 | 2399.99 | 6 | 2463.98 | 263.92
357 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | SM/15224 | 2098.08 | 3 | 2053.62 | 885.6
358 | Neorakhola W/S Mnt. Division | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | SM/16157 | 112.01 | 2 | 109.11 | 0
359 | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME | SM/15269 | 189.49 | 6 | 132.43 | 41.65
360 | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME | SM/15274 | 194.82 | 7 | 131.74 | 20.78
361 | Neorakhola W/S Mnt. Division | PWS Scheme for Maharani Tea Garden | SM/16474 | 465.91 | 2 | 443.48 | 103
362 | Neorakhola W/S Mnt. Division | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 | 485.98 | 5 | 440.03 | 91.32
363 | Neorakhola W/S Mnt. Division | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 | 524.85 | 6 | 508.98 | 107.09
364 | Neorakhola W/S Mnt. Division | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme | SM/16385 | 556.38 | 4 | 545.56 | 108.45
365 | Neorakhola W/S Mnt. Division | BIJANBARI PIPED WATER SUPPLY SCHEME. | SM/15869 | 357.73 | 3 | 341.43 | 75.45
366 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16352 | 705.57 | 3 | 699.26 | 100.6
367 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16628 | 870.77 | 3 | 843.4 | 366.82
368 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16145 | 442.66 | 2 | 419.64 | 258.23
369 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT TARBANDHA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15632 | 0 | 1 | 6.26 | 0
370 | Neorakhola W/S Mnt. Division | SAMALBONG PWSS | SM/18722 | 1305.89 | 2 | 1204.11 | 251.71
371 | Neorakhola W/S Mnt. Division | KANKIBONG PWSS | SM/18992 | 836.23 | 1 | 785.44 | 0
372 | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME | SM/10026 | 1323.79 | 17 | 1320.38 | 233.67
373 | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 | 1079.19 | 10 | 784.32 | 170.16
374 | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/18614 | 1017.38 | 7 | 775.41 | 30.55
375 | Kurseong Division | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | SM/18652 | 1174.35 | 2 | 964.56 | 0
376 | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME | SM/11774 | 452.96 | 7 | 436.52 | 6.36
377 | Siliguri W/S Division | IMPLEMENTATION OF AFFORDABLE IOT SYSTEM AT PASCHIM MADATI WATER SUPPLY SCHEME IN PHANSIDEWA BLOCK UNDER DARJEELING DISTRICT. | null | 0 | 0 | 0 | 0
378 | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dangarvita Piped water Supply Scheme at Kharibari Block | SM/07424 | 70.07 | 0 | 0 | 44.03
379 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Paschim Madati Mouza part of Purba Madati Piped water Supply Scheme (Part-A) | SM/07070 | 44.75 | 1 | 35.92 | 21.95
380 | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Chayan Sing and Bhogbhita village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-B) | SM/07048 | 42.44 | 2 | 1.68 | 16.49
381 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division | SM/10767 | 16.01 | 2 | 14.83 | 7.21
382 | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME | SM/10469 | 647.25 | 9 | 657.18 | 210.18
383 | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME | SM/09829 | 843.24 | 19 | 856.75 | 353.29
384 | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate | SM/10239 | 0 | 2 | 229.2 | 211.08
385 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) | SM/11379 | 23.39 | 4 | 19.91 | 0
386 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar | SM/11382 | 54.99 | 2 | 48.43 | 25.96
387 | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | 122.75 | 4 | 113.3 | 8.92
388 | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/10795 | 0 | 5 | 17.79 | 0
389 | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | 0 | 16 | 214.91 | 120.07
390 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | SM/11324 | 36.13 | 2 | 30.3 | 8.63
391 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. | SM/11325 | 10.69 | 2 | 10.08 | 3.73
392 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA | SM/11328 | 27.54 | 2 | 23.46 | 7.68
393 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling | SM/11309 | 8.98 | 1 | 7.72 | 3.4
394 | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA | SM/11335 | 12.77 | 2 | 9.52 | 6.39
395 | Kurseong Division | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | SM/19038 | 6918 | 1 | 5612.47 | 0
396 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | 233.67 | 2 | 218.97 | 12.5
397 | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME | SM/12799 | 484.93 | 7 | 444.29 | 79.14
398 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 | 32.23 | 4 | 30.55 | 0
399 | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME | SM/12035 | 117.92 | 6 | 96.34 | 1.73
400 | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11350 | 26.38 | 3 | 25.78 | 12.21
401 | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME | SM/12036 | 272.84 | 6 | 178.63 | 98.79
402 | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 192 numbers of school under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | SM/11356 | 0 | 1 | 620.25 | 567.62
403 | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/11361 | 0 | 1 | 97.88 | 93.19
404 | Neorakhola W/S Mnt. Division | Providing functional Household tap connection from existing PWSS at Khaling dhura & Vah Tukbar( Bhutta Kheti) | SM/13352 | 62.01 | 1 | 48.48 | 0
405 | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/12748 | 255.93 | 12 | 164.46 | 97.44
406 | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME | SM/12773 | 513.64 | 7 | 276.91 | 166.47
407 | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) | SM/13509 | 608.67 | 15 | 504.78 | 163.83
408 | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 | 240.06 | 9 | 211.05 | 150.78
409 | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme | SM/13394 | 319.83 | 6 | 273.28 | 44.68
410 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 | 1646.2 | 8 | 1632.37 | 587.42
411 | Neorakhola W/S Mnt. Division | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | SM/16159 | 307.56 | 2 | 288.35 | 67.28
412 | Neorakhola W/S Mnt. Division | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | SM/16160 | 237.91 | 2 | 197.63 | 12.5
413 | Neorakhola W/S Mnt. Division | LODHAMA PIPED WATER SUPPLY SCHEME. | SM/15872 | 178.54 | 3 | 158.3 | 0
414 | Neorakhola W/S Mnt. Division | CHAINPURAY PIPED WATER SUPPLY SCHEME | SM/15881 | 82.28 | 2 | 81.11 | 40
415 | Neorakhola W/S Mnt. Division | HATTA PIPED WATER SUPPLY SCHEME. | SM/15883 | 329.63 | 2 | 279.65 | 0
416 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/15884 | 710.16 | 2 | 491.85 | 166.28
417 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BIRSING PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15856 | 0 | 1 | 6.26 | 0
418 | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16534 | 1531.5 | 2 | 1462.11 | 0
419 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | SM/16386 | 669.48 | 2 | 661.54 | 306.11
420 | Northern Mechanical Division | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GUABARI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15628 | 0 | 1 | 6.26 | 0
421 | Neorakhola W/S Mnt. Division | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | SM/16238 | 133.16 | 2 | 129 | 0
422 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | SM/16627 | 954.9 | 3 | 926.14 | 0
423 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/16629 | 610.28 | 2 | 579.52 | 0
424 | Kurseong Division | PWS Scheme for Selim Hill Tea Garden | SM/15652 | 967.91 | 2 | 912.61 | 192.42
425 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/18282 | 1545.44 | 2 | 1481.43 | 0
426 | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18633 | 1443.98 | 5 | 1384.69 | 654.71
427 | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME | SM/18637 | 1581.9 | 6 | 1409.56 | 153.34
428 | Neorakhola W/S Mnt. Division | GINGLAM & GIELIE TEA GARDEN PWSS | SM/18721 | 1070.75 | 3 | 1068.71 | 304.36
429 | Neorakhola W/S Mnt. Division | HUM TUKDAH KHASMAHAL PWSS | SM/18316 | 1456.69 | 4 | 1223.06 | 515.69
430 | Neorakhola W/S Mnt. Division | PESHOK TEA GARDEN PWSS | SM/18728 | 1054.98 | 3 | 976.15 | 0
431 | Kurseong Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | 3390 | 4 | 3141.92 | 494.94
432 | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME | SM/18421 | 1259.04 | 14 | 1055.65 | 86.21
433 | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/18820 | 2125.19 | 3 | 1974.09 | 379.03
434 | Kurseong Division | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | SM/18917 | 947.7 | 0 | 0 | 0
435 | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING | SM/19177 | 9214.38 | 0 | 0 | 0
436 | Kurseong Division | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | 3073.44 | 2 | 2675.58 | 0
437 | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co | SM/19010 | 0 | 6 | 277.01 | 406.94
438 | Siliguri W/S Division | Regarding Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . | SM/06627 | 0 | 2 | 2.17 | 6.86
439 | Neorakhola W/S Mnt. Division | Proposed Estimate for Construction of Sub - Divisional Water Testing Lab over the existing PHE Division Building at Kurseong | SM/14195 | 0 | 0 | 0 | 0
440 | Neorakhola W/S Mnt. Division | Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). | SM/18270 | 0 | 1 | 45.14 | 18.38
441 | Neorakhola W/S Mnt. Division | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA | SM/12737 | 0 | 6 | 9.48 | 8.28
442 | Siliguri W/S Division | Operational Charges of Darjeeling District Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | null | 0 | 0 | 0 | 0
443 | Kurseong Division | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. | SM/11729 | 0 | 2 | 10.66 | 7.3
444 | Darjeeling Division | Setting up of water testing laboratory at Darjeeling: under Darjeeling Division: PHED:GTA | null | 0 | 0 | 0 | 0
445 | Northern Mechanical Division | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . | SM/14065 | 0 | 7 | 17.45 | 14.39
446 | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. | SM/17179 | 0 | 6 | 8.66 | 6.72
447 | Siliguri W/S Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Siliguri Mahakuma Parishad (SMP) Darjeeling District. | SM/09029 | 0 | 0 | 0 | 37.4
448 | Siliguri W/S Division | Operational Charges Of Darjeeling District Laboratory related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission 2023-24 | SM/19262 | 0 | 0 | 0 | 0
449 | Siliguri W/S Division | ENGAGEMENT OF THIRD PARTY INSPECTION AGENCY (TPIA) FOR QUALITY AND QUANTITY MONITORING OF RURAL WATER SUPPLY SCHEMES UNDER JAL SWAPNA (JJM) PROJECT IN DARJEELING DISTRICT OF WEST BENGAL | null | 0 | 0 | 0 | 0
450 | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | SM/10732 | 0 | 8 | 871.06 | 870.27
451 | Neorakhola W/S Mnt. Division | Collection of Drinking Water Samples from various spot sources, PWSS, Schools, Anganwadis, Health Centres and Springs under Darjeeling Hills for water testing at Sindhap sub-district laboratory Darjeeling managed by Neorakhola water supply and maintenance | SM/15668 | 0 | 1 | 12.75 | 6.41
452 | Darjeeling Division | Setting up of water testing laboratory at Sukhiapokri under Darjeeling Division:PHED:GTA | null | 0 | 0 | 0 | 0
Total |  |  |  | 255130.73 | 0 | 213995 | 55151.94