## Work Order Tracking (Rs. in Lak
Work Order Tracking (Rs. in Lakh)
SL. No. | Division | Scheme | Scheme Sm Code | Sanctioned Cost | No. of Work Orders | Work Value | Payment
1 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Goalgaon Piped Water Supply Scheme at Kushmandi Block | SM/07086 | 90.56 | 2 | 16.06 | 141.67
2 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Deulbari Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08168 | 23.49 | 2 | 23.02 | 0
3 | Balurghat Division | Arrangement of Safe Running Drinking Water Supply to 255 nos. of Schools of Different Blocks in The District of Dakshin Dinajpur. (Phase II) | SM/10213 | 0 | 11 | 539.77 | 446.81
4 | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | 312.87 | 11 | 243.68 | 59.65
5 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10456 | 29.45 | 2 | 7.68 | 8.72
6 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jiapur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12616 | 36.44 | 1 | 36.44 | 0
7 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Ramnarayan Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12619 | 36.75 | 2 | 35.25 | 10.42
8 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Matra Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12623 | 38.89 | 2 | 37.75 | 18.24
9 | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | 820.41 | 10 | 730.07 | 356.33
10 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bajerupahat Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12475 | 34.41 | 1 | 34.41 | 0
11 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Shibrampur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12554 | 39.19 | 1 | 39.19 | 0
12 | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | 609.73 | 6 | 513.07 | 161
13 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bamnahar Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12609 | 39.73 | 2 | 38.17 | 9.29
14 | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | 682.77 | 14 | 619.17 | 454.67
15 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gorahar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12550 | 37.98 | 1 | 37.98 | 0
16 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajdhara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12850 | 39.55 | 3 | 38.3 | 15.37
17 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Banshra Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12965 | 40.72 | 2 | 39.21 | 17.61
18 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Khandara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12970 | 37.57 | 2 | 36.42 | 15.75
19 | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | 353.41 | 6 | 285.18 | 189.34
20 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bhagmaha Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13184 | 36.91 | 1 | 36.91 | 0
21 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Arazi Panishala Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13191 | 38.52 | 1 | 38.52 | 0.07
22 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Itakhor Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12944 | 39.72 | 2 | 38.2 | 10.11
23 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Krishnagar Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12971 | 38.89 | 1 | 36.91 | 3.62
24 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Udaypur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12979 | 35.66 | 1 | 35.66 | 0
25 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Cherapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12920 | 38.89 | 3 | 38.26 | 28.13
26 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Buripukur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13196 | 35.19 | 1 | 35.19 | 0
27 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nayapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12934 | 39.45 | 2 | 38.47 | 21.27
28 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rupain Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12935 | 37.54 | 2 | 37.66 | 2.51
29 | Balurghat Division | Restoration of Pipe Line for providing FHTC in connection with Retrofitting of Kail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) | SM/15169 | 44.91 | 3 | 8.95 | 8.95
30 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Keotsar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12604 | 37.24 | 3 | 36.07 | 14.66
31 | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | 1021.01 | 6 | 852.47 | 414.55
32 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Piakhan Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12459 | 42.13 | 1 | 39.99 | 0
33 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak-Bansi Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12966 | 39.72 | 2 | 38.64 | 19.2
34 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Madhyamkarai Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13193 | 40.02 | 2 | 38.19 | 11.31
35 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | 98.62 | 11 | 102.65 | 166.52
36 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divis | SM/09778 | 19.67 | 3 | 8.68 | 8.68
37 | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone I at Hili Block in the District of Dakshin Dinajpur under Balurghat Di | SM/09781 | 41.16 | 3 | 35.89 | 8.09
38 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/09796 | 379.42 | 13 | 382.23 | 263.13
39 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dharail Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12615 | 40.05 | 2 | 38.38 | 11.34
40 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Majhina Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12617 | 38.23 | 2 | 36.37 | 1.75
41 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barajhara Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12464 | 35.97 | 1 | 35.97 | 0
42 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bejebikair Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12465 | 40.72 | 1 | 38.65 | 0
43 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rankhanpara Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12473 | 36.5 | 1 | 34.65 | 0
44 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Samaspur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12479 | 39.88 | 2 | 38.43 | 15.83
45 | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | 566.55 | 15 | 515.59 | 305.41
46 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jangalpur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12603 | 39.17 | 2 | 37.76 | 19.93
47 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Manipur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12613 | 41 | 3 | 39.48 | 20.26
48 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jagannathpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12857 | 37.08 | 1 | 35.19 | 0
49 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barail Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12861 | 37.18 | 1 | 37.18 | 0
50 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Katnapara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12870 | 36.58 | 1 | 34.72 | 0
51 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Anarpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12964 | 40.05 | 3 | 39.06 | 21.23
52 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gopalpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12968 | 37.41 | 2 | 35.7 | 23.39
53 | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | 771.73 | 13 | 676.1 | 402.97
54 | Balurghat Division | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | 908.41 | 8 | 890.91 | 353.92
55 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhandail Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13186 | 40.3 | 2 | 38.44 | 9.26
56 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08169 | 45.08 | 3 | 46.26 | 41.88
57 | Balurghat Division | Augmentation of Kismat Dapat Trimohini Piped Water Supply Scheme (Zone - I & Zone - II) | SM/13351 | 2419.55 | 14 | 1852.51 | 703.01
58 | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | 866.1 | 7 | 772.99 | 208.78
59 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Randanga Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12939 | 37.58 | 1 | 37.58 | 0
60 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saraipur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12943 | 40.58 | 2 | 38.7 | 3.65
61 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Charla Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12948 | 40.86 | 2 | 38.98 | 12.27
62 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Pasoya Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12973 | 40.02 | 2 | 38.82 | 17.55
63 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Raghunathpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12975 | 35.5 | 1 | 35.5 | 0
64 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gaurangapur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12976 | 37.85 | 1 | 37.85 | 0
65 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Langal Bhanga Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12933 | 37.74 | 2 | 36.31 | 11.38
66 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gangajit Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13205 | 35.97 | 1 | 35.97 | 0
67 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jamirail Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12913 | 40.86 | 2 | 38.98 | 11.66
68 | Balurghat Division | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte. | SM/15558 | 78.15 | 5 | 70.72 | 33.32
69 | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | 1195.59 | 7 | 987.81 | 635.04
70 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jotbasanta Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12954 | 38.56 | 1 | 36.6 | 0
71 | Balurghat Division | Source Augmentation of Dangram Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16562 | 189.43 | 4 | 144.1 | 126.21
72 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Kalikamora Water Supply Schemes at Kushmandi Block of Dakshin Dinajpur District under Malda Mecha | SM/17643 | 0 | 0 | 0 | 0
73 | Balurghat Division | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | 1090.83 | 6 | 869.15 | 212.82
74 | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | 720.9 | 14 | 572.61 | 375.62
75 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Krishna Charan Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12955 | 39.72 | 2 | 38.33 | 13.69
76 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Matizapur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12858 | 38.23 | 2 | 36.38 | 1.94
77 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | SM/07090 | 57.62 | 7 | 60.42 | 89.3
78 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nunail Piped Water Supply Scheme at Balurghat Block | SM/07079 | 72.69 | 2 | 20.64 | 97.01
79 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Badmulukkismat Piped Water Supply Scheme at Balurghat Block | SM/07083 | 73.5 | 1 | 7.64 | 99.57
80 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | 85.05 | 5 | 149.25 | 75.7
81 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Jabaripur Piped Water Supply Scheme | SM/07171 | 31.82 | 1 | 27.64 | 51.47
82 | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | 628.61 | 12 | 538.12 | 203.85
83 | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | 389.86 | 16 | 384.42 | 271.65
84 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10457 | 29.13 | 3 | 29.79 | 7.73
85 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dahuakuri Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12460 | 38.12 | 1 | 38.12 | 0
86 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ranabindul Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12462 | 37.38 | 1 | 37.38 | 0
87 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Elankuri Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12466 | 39.32 | 1 | 39.32 | 0
88 | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | 906.17 | 6 | 806.53 | 151.93
89 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chhota Faizullapur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12477 | 37.04 | 2 | 37.6 | 15.41
90 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mahabari Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12478 | 36.91 | 1 | 36.91 | 0
91 | Balurghat Division | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | 257.53 | 12 | 225.22 | 178.97
92 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandradaula Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12555 | 35.97 | 1 | 35.97 | 0
93 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhaul Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12556 | 38.92 | 1 | 38.92 | 0
94 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barakhail Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12537 | 37.18 | 2 | 37.26 | 12.08
95 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chingra Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12539 | 39.45 | 3 | 38.1 | 15.73
96 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Satais Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12606 | 39.45 | 2 | 37.93 | 13.73
97 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sanihara Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12541 | 38.89 | 2 | 37.09 | 14.85
98 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saidpur Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12546 | 41.14 | 2 | 40.09 | 21.17
99 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bikuch Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12547 | 36.76 | 3 | 36.99 | 15.89
100 | Balurghat Division | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | 984.47 | 8 | 826.9 | 530.71
101 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kasthagar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12551 | 37.04 | 1 | 37.04 | 0
102 | Balurghat Division | Augmentation of Anantapur Piped Water Supply Scheme (Zone-I & Zone-II) at Kushmandi Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) (Phase-III) | SM/12846 | 38.1 | 3 | 22.58 | 21.49
103 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gobarta Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12864 | 41.14 | 2 | 40.3 | 25.27
104 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kanaipur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12960 | 41.71 | 1 | 39.59 | 4.05
105 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gunsi Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12969 | 36.25 | 2 | 35.1 | 14.1
106 | Balurghat Division | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | 339.02 | 7 | 311.2 | 188.87
107 | Balurghat Division | SOBRASYAMPUR PIPED WATER SUPPLY SCHEME | SM/13092 | 339.71 | 5 | 299.72 | 116.07
108 | Balurghat Division | DHULATAIR Piped Water Supply Scheme | SM/12819 | 715.77 | 6 | 652.97 | 421.27
109 | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | 1016.98 | 8 | 931.36 | 142.77
110 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nahara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12972 | 42.13 | 2 | 40.43 | 9.02
111 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kharikadighi Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12924 | 37.98 | 1 | 37.98 | 0
112 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paschim Para Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13199 | 35.82 | 1 | 35.82 | 0
113 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Haripur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13202 | 35.35 | 1 | 35.35 | 0
114 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uddhabpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12952 | 37.41 | 2 | 35.66 | 9.91
115 | Balurghat Division | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Poradanga Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12925 | 41.85 | 4 | 43.27 | 23.24
116 | Balurghat Division | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barail Mouza of Kushmandii Block in the District of Dakshin Dinajpur. | SM/12929 | 37.9 | 2 | 36.17 | 17.52
117 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jugati Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12932 | 40.02 | 4 | 42.28 | 29.76
118 | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | 1263.54 | 13 | 1120.6 | 710.77
119 | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | 954.48 | 8 | 817.73 | 445
120 | Balurghat Division | Restoration of Pipe Line for Retrofitting of FHTC under Kasba Bairhatta Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15164 | 69.5 | 3 | 41.75 | 5.34
121 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandmoua Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12967 | 39.31 | 2 | 38.13 | 17.02
122 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Khidirpur Water Supply Schemes at Balurghat Block of Dakshin Dinajpur District under Malda Mecha | SM/17637 | 0 | 0 | 0 | 0
123 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Anantapur (Zone-I) Water Supply Schemes at Kushmandi Block of Dakshin Dinajpur District under Mal | SM/17644 | 0 | 0 | 0 | 0
124 | Balurghat Division | UTTAR KHANPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12702 | 713.05 | 6 | 626.05 | 236.48
125 | Balurghat Division | MARGRAM Piped Water Supply Scheme | SM/16269 | 577.5 | 4 | 453.98 | 120.24
126 | Balurghat Division | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ranipur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12926 | 40.3 | 2 | 38.6 | 15.38
127 | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | 23387.79 | 28 | 22738.5 | 6506.9
128 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block | SM/07078 | 19.21 | 3 | 5.68 | 32.06
129 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09779 | 38.71 | 4 | 37.4 | 34.13
130 | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | 593.3 | 16 | 509.77 | 295.66
131 | Balurghat Division | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | 347.68 | 6 | 288.73 | 260.2
132 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10453 | 13.77 | 1 | 3.04 | 3.04
133 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Srirampur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12468 | 37.85 | 1 | 37.85 | 0
134 | Balurghat Division | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | 889.01 | 7 | 818.17 | 451.04
135 | Balurghat Division | JANTIGRAM Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12706 | 813.24 | 6 | 704.25 | 325.05
136 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Khetab Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12558 | 36.25 | 3 | 35.05 | 14.21
137 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Hatisala Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12602 | 40.58 | 2 | 39.49 | 28.26
138 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kodla Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12605 | 39.55 | 2 | 38.21 | 21.52
139 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uchhakapur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12608 | 39.73 | 2 | 38.08 | 11.96
140 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Darail Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12544 | 39.55 | 1 | 37.54 | 0
141 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kajialsi Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12545 | 41.29 | 2 | 40.51 | 28.78
142 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bishnupur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12852 | 40.21 | 2 | 39.08 | 18.79
143 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Bhagaban Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12854 | 39.59 | 3 | 38.35 | 15.72
144 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gayespur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12856 | 40.21 | 2 | 39.05 | 16.91
145 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Par Sahazadpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12865 | 40.21 | 2 | 39.37 | 26.58
146 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Majhina of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12871 | 40.05 | 1 | 38.01 | 0
147 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Mulahati Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12962 | 36.75 | 2 | 35.33 | 9.22
148 | Balurghat Division | Retrofitting of Pundari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-II] | SM/13019 | 43.3 | 3 | 23.18 | 20.31
149 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Porabagdol Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12917 | 38.65 | 1 | 38.65 | 0
150 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chapapara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13185 | 38.07 | 3 | 36.35 | 8.96
151 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jagannathpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13187 | 35.35 | 1 | 35.35 | 0
152 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Maulai Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12941 | 41.85 | 1 | 39.72 | 4.21
153 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baramahar Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12947 | 38.89 | 2 | 37.48 | 11.47
154 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chausha Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12980 | 42.13 | 1 | 39.99 | 1.84
155 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Raghunathpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13194 | 36.91 | 1 | 36.91 | 0
156 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nehal Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12958 | 40.02 | 2 | 38.18 | 4.06
157 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jadabpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12936 | 37.54 | 1 | 37.54 | 0
158 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | 82.29 | 9 | 79.88 | 122.91
159 | Balurghat Division | Source Augmentation of Nawapara Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16208 | 66.07 | 3 | 47.65 | 37.43
160 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Siala Water Supply Schemes at Balurghat Block of Dakshin Dinajpur District under Malda Mechanical | SM/17639 | 0 | 0 | 0 | 0
161 | Malda Mechanical Division | Design, Supply and Installation of different capacity Solar Power Plant at various water work station of Tapan Sub Surface Water Based Piped Water Supply Scheme with Net Metering Arrangement, Monitoring System in the district of Dakshin Dinajpur under Mal | SM/17675 | 0 | 1 | 111.17 | 0
162 | Balurghat Division | JANGALPUR PWSS | SM/18632 | 1081.76 | 7 | 979.2 | 666.89
163 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalibari Piped Water Supply Scheme at Balurghat Block | SM/07082 | 77.55 | 1 | 72.87 | 96.7
164 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Panjul Piped Water Supply Scheme at Hili Block | SM/07085 | 90.12 | 3 | 98.31 | 134.67
165 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Khidirpur Piped Water Supply Scheme at Balurghat Block | SM/07087 | 91.37 | 1 | 82.42 | 157.51
166 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | 53.14 | 5 | 52.16 | 93.16
167 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08166 | 25.6 | 7 | 60.66 | 22.41
168 | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P. | SM/09784 | 67.27 | 2 | 7.77 | 6.31
169 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09786 | 17.57 | 4 | 17.31 | 17.31
170 | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | 301.84 | 13 | 153.03 | 209.48
171 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Debrabari Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12601 | 37.98 | 1 | 37.98 | 0
172 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chaurapara Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12600 | 41.85 | 2 | 40.79 | 22.7
173 | Balurghat Division | Providing Functional House Hold Tap Connection(part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09889 | 31.57 | 4 | 32.11 | 27.31
174 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kuarsai Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12471 | 40.58 | 1 | 38.52 | 0
175 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Biralipara Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12476 | 38.56 | 1 | 36.6 | 15.96
176 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jaydebpur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12481 | 39.19 | 1 | 39.19 | 0
177 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chhiashi Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12538 | 37.57 | 2 | 36.29 | 20.93
178 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chakpara Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12548 | 38.17 | 1 | 38.17 | 0
179 | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | 937.75 | 10 | 805.49 | 484.56
180 | Balurghat Division | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | 920.09 | 5 | 744.28 | 32.85
181 | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | 836.28 | 6 | 747.73 | 320.92
182 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bayrapara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12862 | 40.21 | 2 | 38.57 | 8.25
183 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bijalipara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12863 | 37.23 | 1 | 37.23 | 0
184 | Balurghat Division | Augmentation of Domran Piped Water Supply Scheme at Hilli Block, in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) | SM/12847 | 22.68 | 2 | 21.86 | 20.76
185 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uchhana Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12866 | 40.58 | 2 | 39.05 | 10.91
186 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chakrasail Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12867 | 41 | 1 | 38.92 | 0
187 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mudafat Kochapara Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12961 | 38.07 | 1 | 36.13 | 10.18
188 | Balurghat Division | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | 448.91 | 11 | 239.35 | 213.98
189 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nij Raghunathpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12915 | 36.5 | 3 | 38.63 | 15.92
190 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Basudebpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13183 | 38.79 | 1 | 38.79 | 0
191 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Punat Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13190 | 36.29 | 1 | 36.29 | 0
192 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jotgora Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12945 | 39.88 | 2 | 38.32 | 24.4
193 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Patit Pukur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12977 | 39.05 | 1 | 39.05 | 0
194 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kalancha Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12922 | 39.06 | 2 | 37.65 | 11.7
195 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nambhail Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13198 | 37.7 | 1 | 37.7 | 0
196 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ekdala Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13204 | 36.91 | 1 | 36.91 | 0
197 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Phulat (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12951 | 39.59 | 2 | 38.09 | 10.32
198 | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | 1539.58 | 14 | 1385.31 | 999.24
199 | Balurghat Division | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | 707.27 | 6 | 597.73 | 239.24
200 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Panitara Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12872 | 38.4 | 3 | 37.3 | 18.32
201 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Kalibari Water Supply Schemes at Balurghat Block of Dakshin Dinajpur District under Malda Mechani | SM/17636 | 0 | 0 | 0 | 0
202 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Bilbarail Water Supply Schemes at Banshihari Block of Dakshin Dinajpur District under Malda Mecha | SM/17646 | 0 | 0 | 0 | 0
203 | Malda Mechanical Division | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for twenty four nos. PWSS in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | SM/17180 | 0 | 5 | 166.06 | 30.26
204 | Malda Mechanical Division | Design, Supply and Installation of different capacity Solar Power Plant at various water work station of Gangarampur Sub Surface Water Based Piped Water Supply Scheme with Net Metering Arrangement, Monitoring System in the district of Dakshin Dinajpur un | SM/17676 | 0 | 1 | 110.01 | 0
205 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Auggumentation for Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09782 | 33.42 | 2 | 24.69 | 2.83
206 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nituttarpara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12916 | 41 | 2 | 39.12 | 12.37
207 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Darajpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12982 | 39.31 | 3 | 37.78 | 22.88
208 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Salgaon Piped Water Supply Scheme at Balurghat Block | SM/07084 | 67.26 | 2 | 59.6 | 45.31
209 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bilbarail piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur(PHASE - II) | SM/08167 | 43.32 | 2 | 72.17 | 68.88
210 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | 259.01 | 5 | 243.35 | 281.84
211 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Buniadpur Piped Water Supply Scheme at Bansihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10458 | 20.16 | 1 | 3.58 | 3.58
212 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | 1780.97 | 39 | 1714.67 | 989.45
213 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | 63.61 | 9 | 61.22 | 96.53
214 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kadmathail Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12620 | 38.38 | 1 | 38.38 | 0
215 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kismat Jasahar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12622 | 38.73 | 2 | 37.78 | 22.25
216 | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | 476.08 | 11 | 459.26 | 331.57
217 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ojantor Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12467 | 41 | 1 | 38.92 | 0
218 | Balurghat Division | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | 871.49 | 6 | 780.52 | 174.31
219 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sankarpur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12474 | 34.65 | 2 | 34.86 | 15.51
220 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Taksail Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12553 | 38.17 | 1 | 38.17 | 0
221 | Balurghat Division | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | 341.9 | 9 | 268.28 | 145.82
222 | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | 958.58 | 7 | 815.3 | 446.72
223 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bodra Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12853 | 40.05 | 3 | 38.88 | 17.79
224 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bafra Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12860 | 39.59 | 1 | 39.59 | 0
225 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dangapara Belua (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12959 | 38.07 | 1 | 36.13 | 11.02
226 | Balurghat Division | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | SM/13018 | 26.55 | 4 | 13.9 | 13.13
227 | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | 515.05 | 10 | 467.56 | 186.09
228 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajapur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12918 | 39.45 | 1 | 37.45 | 7.1
229 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paptahar Bhaktipur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13189 | 37.98 | 1 | 37.98 | 0
230 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Radhakrishnapur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12974 | 42.13 | 3 | 41.28 | 26.19
231 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Saiyadpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12978 | 41.29 | 2 | 39.35 | 3.25
232 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baghna Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12919 | 38.4 | 3 | 37.26 | 16.48
233 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Angaripara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13195 | 37.71 | 1 | 37.71 | 0
234 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Barakafurchand Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13200 | 38.52 | 1 | 38.52 | 0
235 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bighor Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13201 | 35.35 | 1 | 35.35 | 0
236 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Baje Chahatpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12950 | 37.24 | 2 | 36.57 | 24.8
237 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mahakhor Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12957 | 40.86 | 1 | 38.79 | 0
238 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Thalsama Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12912 | 40.44 | 3 | 38.92 | 17.53
239 | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | 1342.16 | 11 | 1191.19 | 437.76
240 | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | 492.23 | 5 | 429.56 | 249.79
241 | Balurghat Division | MAHADIPUR Piped Water Supply Scheme | SM/16251 | 874.11 | 5 | 766.64 | 124.44
242 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Deulbari Water Supply Schemes at Kushmandi Block of Dakshin Dinajpur District under Malda Mechani | SM/17642 | 0 | 0 | 0 | 0
243 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Shibpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12869 | 38.07 | 1 | 36.13 | 0
244 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Madanpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12849 | 39.06 | 1 | 37.07 | 21.96
245 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Bhikanpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13192 | 42.13 | 2 | 40.18 | 10.93
246 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Siala Piped Water Supply Scheme at Balurghat Block | SM/07088 | 98.96 | 2 | 93.6 | 160.89
247 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Alipur Piped Water Supply Scheme at Balurghat Block | SM/07092 | 59.06 | 2 | 53.23 | 82.44
248 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dangram Piped Water Supply Scheme at Harirampur Block | SM/07081 | 89.01 | 2 | 74.64 | 116.26
249 | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone II at Hili Block in the District of Dakshin Dinajpur under Balurghat | SM/09780 | 63.82 | 4 | 59.06 | 8.77
250 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09785 | 38.03 | 4 | 35.82 | 7.01
251 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | SM/10516 | 999.3 | 20 | 896.05 | 4.08
252 | Balurghat Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Balurghat & Banshihari Block in the District of Dakshin Dinajpur. | SM/10644 | 1021.88 | 3 | 977.44 | 196.31
253 | Balurghat Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Tapan Block in the District of Dakshin Dinajpur. | SM/10645 | 645.81 | 2 | 613.17 | 25.43
254 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Tursail Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12614 | 41.43 | 3 | 39.84 | 19.73
255 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Palashdanga Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12618 | 42.13 | 2 | 40.45 | 13.26
256 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kasipur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12621 | 39.39 | 2 | 37.58 | 19.63
257 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sardarpur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12463 | 37.07 | 1 | 37.07 | 0
258 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jadupur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12470 | 40.05 | 1 | 38.01 | 3.97
259 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paschim Mustafapur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12557 | 39.32 | 1 | 39.32 | 10.64
260 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chakismail Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12559 | 40.21 | 3 | 38.98 | 17.51
261 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kutubpur Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12540 | 40.44 | 2 | 38.55 | 6.33
262 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chiknaikuri Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12549 | 38.73 | 3 | 37.6 | 17.44
263 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Purbba Maheshpur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12552 | 36.6 | 1 | 36.6 | 9.76
264 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak-Behetair Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12855 | 38.73 | 3 | 37.69 | 19.01
265 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sarenbari Mouza of Hili Block in the District of Dakshin Dinajpur. | SM/12963 | 36.75 | 3 | 35.68 | 19.55
266 | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | 626.93 | 8 | 589.5 | 285.88
267 | Balurghat Division | TRIKUL Piped Water Supply Scheme | SM/12817 | 315.25 | 7 | 287.06 | 82.02
268 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Basudebpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12940 | 37.85 | 1 | 37.85 | 0
269 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Palasbari Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12942 | 35.19 | 1 | 35.19 | 0
270 | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | 1474.24 | 12 | 1307.18 | 520.96
271 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Abjalpur (I) Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12949 | 36.42 | 2 | 34.72 | 9.33
272 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Asrafpur Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12953 | 38.89 | 3 | 37.34 | 8.77
273 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dhadarang Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12931 | 40.02 | 2 | 38.84 | 17.96
274 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mastahar Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12914 | 39.73 | 3 | 41.33 | 8.81
275 | Balurghat Division | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | 1242.63 | 7 | 1067.32 | 680.77
276 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nadipur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12981 | 39.59 | 2 | 37.98 | 29.91
277 | Balurghat Division | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15202 | 72.98 | 4 | 54.79 | 19.56
278 | Balurghat Division | Restoration of Pipe Line for Retrofitting of FHTC under Majhigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15204 | 35.3 | 2 | 22.91 | 22.91
279 | Balurghat Division | Improvement of Siala Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Jal Jeevan Mission Programme. | SM/15174 | 20.34 | 1 | 18.69 | 0
280 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Mahindra Water Supply Schemes at Harirampur Block of Dakshin Dinajpur District under Malda Mechan | SM/17641 | 0 | 0 | 0 | 0
281 | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | 907.89 | 9 | 775.03 | 529.58
282 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Harirampur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12612 | 40.05 | 2 | 38.78 | 17.38
283 | Balurghat Division | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Sindur Muchhi Mouza of Kushmandii Block in the District of Dakshin Dinajpur. | SM/12928 | 41.56 | 4 | 43.7 | 22.59
284 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Khamrail Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12938 | 38.52 | 1 | 38.52 | 0
285 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Purba Hariharpur Piped Water Supply Scheme | SM/07170 | 15.8 | 2 | 15.01 | 13.34
286 | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09783 | 22.15 | 4 | 18.07 | 17.28
287 | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | 592.5 | 12 | 472.53 | 294.62
288 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering D | SM/10452 | 22.98 | 3 | 24.07 | 6.87
289 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10454 | 27.07 | 3 | 33.08 | 24.2
290 | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10455 | 18.45 | 3 | 25.42 | 7.82
291 | Balurghat Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Kumarganj, Kushmandi & Tapan Block in the District of Dakshin Dinajpur. | SM/10646 | 1022.75 | 3 | 975.8 | 144.57
292 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Rajapur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12461 | 39.17 | 2 | 37.38 | 8.68
293 | Balurghat Division | Ground Water Based Mini Piped Water Supply Schemes (Maximum 50 Household) at Banshihari, Gangarampur, Harirampur, Hili & Kumarganj Block in the District of Dakshin Dinajpur. | SM/10813 | 1032.88 | 3 | 782.26 | 102.32
294 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gerul Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12469 | 42.13 | 1 | 39.99 | 0
295 | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Harigaon Piped Water Supply Scheme at Balurghat Block | SM/07080 | 60.87 | 3 | 13.2 | 70.29
296 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Paharpur Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12472 | 39.59 | 2 | 37.75 | 7.74
297 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Vstair Mouza of Bansihari Block in the District of Dakshin Dinajpur. | SM/12480 | 40.58 | 1 | 38.52 | 0
298 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chak Sirdhar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12560 | 36.91 | 1 | 36.91 | 0
299 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Satihar Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12607 | 38.23 | 1 | 36.29 | 0
300 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dasarai Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12610 | 35.97 | 1 | 35.97 | 0
301 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gunjarpur Mouza of Balurghat Block in the District of Dakshin Dinajpur. | SM/12611 | 39.31 | 3 | 38.17 | 16.99
302 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Tulsipur Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12542 | 41.29 | 2 | 40.4 | 27.2
303 | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | 1047.59 | 10 | 922.1 | 481.54
304 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Setor Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12851 | 36.91 | 1 | 36.91 | 0
305 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Mominpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12859 | 40.86 | 3 | 40.03 | 27.17
306 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kamdebpur Mouza of Kumarganj Block in the District of Dakshin Dinajpur. | SM/12868 | 40.72 | 1 | 38.65 | 0
307 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Lakshmantara Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13188 | 41.85 | 3 | 40.15 | 20.51
308 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jafarpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12937 | 37.31 | 1 | 37.31 | 0
309 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Nikharpara Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12946 | 36.42 | 2 | 34.98 | 8.45
310 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Jaherpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12921 | 38.73 | 2 | 37.33 | 23.25
311 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Kashimpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12923 | 40.58 | 3 | 39.12 | 25.77
312 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Ibrahimpur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13197 | 37.23 | 1 | 37.23 | 0
313 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Dopitha Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13203 | 37.85 | 1 | 37.85 | 0
314 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Lakshmipur Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12956 | 38.4 | 2 | 36.79 | 6.98
315 | Balurghat Division | Ground Water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Silimpur Mouza of Kushmandii Block in the District of Dakshin Dinajpur. | SM/12927 | 40.87 | 2 | 39.32 | 19.04
316 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Birampur Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/12930 | 41.57 | 2 | 39.65 | 11.16
317 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Gobrabil Mouza of Kushmandi Block in the District of Dakshin Dinajpur. | SM/13206 | 38.38 | 1 | 38.38 | 0
318 | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | 1488.58 | 14 | 1312.31 | 1005.69
319 | Balurghat Division | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | SM/16207 | 77.02 | 3 | 39.94 | 38.94
320 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Salgaon Water Supply Schemes at Balurghat Block of Dakshin Dinajpur District under Malda Mechanic | SM/17638 | 0 | 0 | 0 | 0
321 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Alipur Water Supply Schemes at Balurghat Block of Dakshin Dinajpur District under Malda Mechanica | SM/17640 | 0 | 0 | 0 | 0
322 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Karai Water Supply Schemes at Banshihari Block of Dakshin Dinajpur District under Malda Mechanica | SM/17645 | 0 | 0 | 0 | 0
323 | Malda Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Panjul Water Supply Schemes at Hili Block of Dakshin Dinajpur District under Malda Mechanical Div | SM/17647 | 0 | 0 | 0 | 0
324 | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Chandipur Mouza of Balurghat Block in the District of Dakshin Dinajpur | SM/12543 | 37.38 | 2 | 38.44 | 22.39
325 | Balurghat Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/08979 | 0 | 3 | 8.9 | 8.9
326 | Balurghat Division | Procurement of Consumables i.c.w. OMAS for Water Testing Laboratories in the District of Dakshin Dinajpur under JJM (For 01 Year) | SM/11888 | 0 | 1 | 15.46 | 15.46
327 | Balurghat Division | DPR regarding procurement of Chemicals & Consumables, Glassware etc. required for smooth running of Laboratory. | SM/06625 | 0 | 3 | 16.22 | 48.12
328 | Balurghat Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Dakshin Dinajpur District. | SM/08976 | 0 | 0 | 0 | 167.04
329 | Balurghat Division | Supply, Delivery and Installation of Computer & Peripherals for Official use under Office of the Superintending Engineer, NBC-II, PHE Dte., and Balurghat Division, PHE Dte. | SM/10112 | 0 | 1 | 10.91 | 11.67
330 | Balurghat Division | Detail Project Report for Operational charges of PHED & NGO Managed Laboratories in the district of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance for 01 (One) year. | SM/18145 | 0 | 36 | 27.58 | 27.58
331 | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | 0 | 3 | 13.1 | 9.2
332 | Balurghat Division | DPR on IEC Activities and Mass Awareness Generation (Support Activities) for awareness of Rural community on WASH at different Blocks in Dakshin Dinajpur District under Jal Jeevan Mission (JJM) |  | 0 | 0 | 0 | 0
333 | Balurghat Division | Supply, Delivery and installation of Computer & Peripherals for official use under office of the Superintending Engineer, North Bengl Circle-II & Executive Engineer, Balurghat Division, PHE Dte. |  | 0 | 0 | 0 | 0
334 | Balurghat Division | Procurement of Chemicals & consumables Glassware etc. required for smooth running of 05 nos. laboratories in the district of Dakshin Dinajpur. | SM/10515 | 0 | 4 | 14.77 | 14.77
335 | Balurghat Division | COLLECTION, TESTING & UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKs w.r.t. WATER QUALITY MONITORING & SURVEILLANCE UNDER JJM IN THE DISTRICT OF DAKSHIN DINAJPUR UNDER BALURGHAT DIVISION PHE DTE. | SM/18142 | 0 | 2 | 10.2 | 11.21
Total |  |  |  | 85148.91 | 0 | 78109.56 | 32763.79