## Work Order Tracking (Rs. in Lak
Work Order Tracking (Rs. in Lakh)
SL. No. | Division | Scheme | Scheme Sm Code | Sanctioned Cost | No. of Work Orders | Work Value | Payment
1 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-J) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08107 | 383.46 | 1 | 259.69 | 0
2 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kusbaria (314722) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | SM/07912 | 105.04 | 1 | 73.51 | 68.95
3 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur Chak ( 314703 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District | SM/07914 | 63.09 | 1 | 43.61 | 0
4 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric | SM/07917 | 97.32 | 6 | 115.89 | 69.64
5 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme | SM/07226 | 87.91 | 2 | 87.36 | 43.95
6 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M | SM/07924 | 66.03 | 7 | 38.45 | 38.17
7 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of | SM/07515 | 89.95 | 3 | 37.33 | 25.19
8 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District | SM/07273 | 44.21 | 7 | 97.36 | 39.2
9 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) | SM/07725 | 119.17 | 3 | 118.18 | 74.44
10 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II | SM/08109 | 886.86 | 11 | 810.73 | 558.72
11 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08111 | 1011.33 | 15 | 902.44 | 389.85
12 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs | SM/07277 | 51.55 | 6 | 50.91 | 22.48
13 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff | SM/07285 | 87.45 | 3 | 78.32 | 50.61
14 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu | SM/07286 | 98.3 | 2 | 103.78 | 46.29
15 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s | SM/07234 | 87.8 | 2 | 93.67 | 60.85
16 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA | SM/07685 | 146.33 | 2 | 104.96 | 58.55
17 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) | SM/07699 | 96.83 | 2 | 95.83 | 48.42
18 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07296 | 90.93 | 5 | 112.13 | 75.7
19 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | 63.33 | 9 | 55.95 | 46.24
20 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) | SM/07668 | 241.26 | 6 | 223.96 | 115.1
21 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR | SM/07508 | 58.94 | 3 | 81.77 | 12.92
22 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa | SM/07695 | 119.21 | 3 | 117.78 | 103.23
23 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jhikra (Code-314512), Ranitala (Code-314513) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-A) Un | SM/07795 | 83.47 | 1 | 66.83 | 53.37
24 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In | SM/07788 | 99.99 | 2 | 90.07 | 80.04
25 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected | SM/08185 | 329.04 | 5 | 226.7 | 18.03
26 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area | SM/08199 | 386.05 | 4 | 85.11 | 70.93
27 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U | SM/08902 | 304.14 | 3 | 224.54 | 207.87
28 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh | SM/08271 | 423.18 | 5 | 280.16 | 168.69
29 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | SM/08278 | 517.99 | 7 | 359.13 | 251.23
30 | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad | SM/09743 | 251.5 | 7 | 114.35 | 18.23
31 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | SM/09748 | 157.21 | 3 | 156.77 | 0
32 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u | SM/09738 | 54.13 | 2 | 68.62 | 27.07
33 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc | SM/08688 | 461.79 | 13 | 337.64 | 171.79
34 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09836 | 32.06 | 5 | 47.47 | 30.3
35 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debottar Lakshminarayanpur ( 314678 ) of Jitpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District und | SM/09843 | 44.72 | 0 | 0 | 0
36 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba | SM/09762 | 85.85 | 8 | 147.62 | 35.06
37 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M | SM/09765 | 79.54 | 32 | 55.14 | 21.8
38 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | 107.76 | 12 | 140.38 | 39.98
39 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | 480.94 | 8 | 778.61 | 264.46
40 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate | SM/07796 | 92.37 | 2 | 91.72 | 46.18
41 | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | 441.86 | 14 | 372.22 | 85.76
42 | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | 965.82 | 11 | 719.49 | 227.61
43 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10997 | 332.05 | 3 | 320.03 | 68.22
44 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | 498.55 | 14 | 522.86 | 45.75
45 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. | SM/11161 | 205.19 | 3 | 62.87 | 0
46 | Murshidabad Division | Source Augmentation of Functional Household Tap Connections (FHTC) of Mouza Habaspur (314487) of Habaspur under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Bhagwangola-I Block of Murshidabad District Under Murshidabad Division Phe | SM/11162 | 480.32 | 1 | 7.61 | 0
47 | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11714 | 907.4 | 5 | 265.43 | 11.34
48 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) | SM/07221 | 62.74 | 3 | 62.65 | 48.51
49 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | SM/08908 | 384.82 | 3 | 353.57 | 301.21
50 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744,314745,314746,314747,314753,314754,314755,314756) of Purusottampur under ground w | SM/11216 | 162.44 | 2 | 36.16 | 0
51 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Sinkaipur (314775) of Azamatpur Ground water based water supply scheme for arsenic affected areas of Raninagar - I Block in Murshidabad District under Murshidabad Division, P.H.E.D | SM/11219 | 72.82 | 1 | 5.14 | 0
52 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | 930.14 | 6 | 466.91 | 91.98
53 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11569 | 512.1 | 6 | 391.44 | 104.5
54 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Amarkunda, Bagor, Nandigram, Madhunia, Chayan Nagar, Sankuria, Rainda ( ) of Amarkundu under Ground Water Based Water Supply Scheme for arsenic affected areas of Nabagram Block of | SM/11230 | 273.1 | 2 | 21.15 | 0
55 | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | 640.11 | 9 | 633.98 | 39.33
56 | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | 770.8 | 6 | 662.88 | 69.36
57 | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | 721.32 | 13 | 562.08 | 144.9
58 | Berhampur Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | 649.29 | 12 | 506.95 | 12.81
59 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14832 | 821.37 | 9 | 485.76 | 4.24
60 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13993 | 689.2 | 4 | 252.65 | 0
61 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | 564.45 | 8 | 321.32 | 25.93
62 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. | SM/14630 | 466.17 | 7 | 267.76 | 67.37
63 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14633 | 573.57 | 7 | 317.22 | 12.79
64 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I | SM/15230 | 540.38 | 7 | 286.46 | 3.88
65 | Berhampur Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III | SM/15231 | 527.09 | 6 | 403.11 | 3.87
66 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . | SM/15234 | 624.73 | 10 | 416.8 | 6.62
67 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JALANGI Zone-I, Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. | SM/15282 | 0 | 1 | 6.39 | 0
68 | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | 828.25 | 9 | 463.27 | 2.57
69 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . | SM/14738 | 857.82 | 8 | 439.46 | 45.8
70 | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | 853.48 | 8 | 418.51 | 2.08
71 | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/16248 | 394.39 | 4 | 322.14 | 0
72 | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15838 | 745.29 | 5 | 719.99 | 142.31
73 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at EDRAKPUR Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | SM/15327 | 0 | 1 | 6.38 | 0
74 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at CHANDPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | SM/15331 | 0 | 1 | 6.39 | 0
75 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Manigram Ground water Based PWSS, Block-Sagardighi , Dist- Murshidabad under MEDB, PHE Dte. | SM/15345 | 0 | 1 | 6.39 | 0
76 | Berhampur M/E Division | Implementation of affordable IoT System at Amorkundu water supply Scheme in Nabgram Block, Dist- Murshidabad. | SM/15703 | 0 | 0 | 0 | 0
77 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III | SM/07514 | 45.43 | 2 | 47.42 | 22.71
78 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16430 | 75.32 | 3 | 62.67 | 0
79 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone- III, Block- Lalgola, District- Murshidabad. | SM/16434 | 40.62 | 2 | 36.61 | 0
80 | Berhampur M/E Division | Implementation of affordable IoT System at Brahamottar Manikchak water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/16006 | 0 | 0 | 0 | 0
81 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Pashchim Gobindapur, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16438 | 34.17 | 2 | 30.1 | 0
82 | Murshidabad Division | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. | SM/16443 | 81.23 | 4 | 73.54 | 0
83 | Berhampur M/E Division | Implementation of affordable IoT System at Jumra Nayagram water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15999 | 0 | 0 | 0 | 0
84 | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | 478.54 | 3 | 93.89 | 3.68
85 | Murshidabad Division | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16112 | 226.02 | 6 | 189.6 | 5.34
86 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-III, Block- Berhampore, District- Murshidabad. | SM/16045 | 40.62 | 2 | 36.62 | 0
87 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. | SM/16176 | 133.85 | 6 | 103.4 | 3.7
88 | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16171 | 819.74 | 3 | 469.39 | 0
89 | Berhampur M/E Division | Implementation of affordable IoT System at Teghari water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15708 | 0 | 0 | 0 | 0
90 | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/15922 | 522.7 | 5 | 315.62 | 90.54
91 | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | 856.53 | 8 | 517.53 | 92.91
92 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Darura, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16212 | 32.81 | 2 | 29.94 | 0
93 | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. | SM/16215 | 162.46 | 8 | 147.09 | 0
94 | Berhampur M/E Division | Implementation of affordable IoT System at Kasba-Bahadurpur water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15988 | 0 | 0 | 0 | 0
95 | Berhampur M/E Division | Implementation of affordable IoT System at Kakramari,Zone-I & II water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15735 | 0 | 0 | 0 | 0
96 | Berhampur M/E Division | Implementation of affordable IoT System at Jaykrishnapur water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15662 | 0 | 0 | 0 | 0
97 | Berhampur Division I | KESABPUR AND ADJOINING MOUJAS PWSS | SM/16788 | 661.59 | 7 | 388.85 | 43.74
98 | Berhampur M/E Division | Implementation of affordable IoT System at Prosadpur, Zone-I&II water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15681 | 0 | 0 | 0 | 0
99 | Murshidabad Division | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15743 | 480.14 | 4 | 419.21 | 0
100 | Berhampur M/E Division | Implementation of affordable IoT System at Goukhana water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/16039 | 0 | 0 | 0 | 0
101 | Berhampur M/E Division | Implementation of affordable IoT System at Kisorepur water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15677 | 0 | 0 | 0 | 0
102 | Murshidabad Division | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | 255.65 | 5 | 206.24 | 2.15
103 | Berhampur M/E Division | Implementation of affordable IoT System at Mirzapur water supply Scheme in Raghunathganj-I Block, Dist- Murshidabad. | SM/15719 | 0 | 0 | 0 | 0
104 | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. | SM/15745 | 558.5 | 5 | 348 | 6.39
105 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16769 | 220.12 | 4 | 200.39 | 3.25
106 | Berhampur Division I | DIAR FATEPUR PWSS | SM/16781 | 915.29 | 8 | 588.36 | 99.48
107 | Berhampur Division I | SHUKUR PUKUR PWSS | SM/16782 | 391.07 | 7 | 160.13 | 7.28
108 | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | 587.32 | 3 | 216.69 | 67.3
109 | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16870 | 945.91 | 6 | 622.46 | 11.16
110 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | 863.23 | 8 | 165.09 | 14.65
111 | Berhampur M/E Division | Implementation of affordable IoT System at Char Mahula water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15704 | 0 | 0 | 0 | 0
112 | Berhampur M/E Division | Implementation of affordable IoT System at Mithipur water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15717 | 0 | 0 | 0 | 0
113 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme | SM/07227 | 92.47 | 3 | 62.34 | 74.36
114 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18384 | 2055.8 | 5 | 955.24 | 0
115 | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. | SM/18555 | 1047.42 | 8 | 633.91 | 7.13
116 | Murshidabad Division | Retrofitting of Ground Water Based Water Supply Scheme for Kamalakantapur and its Adjoining Mouzas to provided last mile connectivety and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/18488 | 135.04 | 1 | 80.18 | 0
117 | Murshidabad Division | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. | SM/18691 | 1102.97 | 5 | 836.28 | 0
118 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18736 | 1945.44 | 9 | 850.38 | 0
119 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18740 | 553.64 | 3 | 311.84 | 30.99
120 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/18756 | 974.86 | 7 | 469.67 | 33.06
121 | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. | SM/18704 | 1031.59 | 8 | 587.41 | 89.82
122 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- | SM/08106 | 360.94 | 5 | 354.56 | 129.61
123 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/07918 | 79.52 | 3 | 54.11 | 47.22
124 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme | SM/07224 | 52.11 | 3 | 51.61 | 30.04
125 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07513 | 61.91 | 7 | 76.71 | 48.5
126 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) | SM/07670 | 155.88 | 7 | 179.5 | 72.78
127 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) | SM/07689 | 32.25 | 3 | 28.45 | 23.33
128 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | 94.89 | 4 | 92.77 | 57.27
129 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( | SM/08110 | 1021.1 | 15 | 1006.65 | 385.62
130 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- | SM/08116 | 823.92 | 11 | 735.36 | 578.99
131 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Digha (VillageCode-314460) under command area under Digha ground water supply scheme (Part-A) | SM/06975 | 86.87 | 1 | 71.28 | 29.55
132 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate | SM/06976 | 72.72 | 3 | 64.2 | 9.78
133 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kulberia Village (Code-315685) Under Command Area Of Andulberia Ground Water Supply Scheme (Part-A) | SM/07696 | 57.19 | 1 | 43.67 | 28.6
134 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur | SM/07664 | 183.02 | 13 | 136.26 | 42.3
135 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part | SM/07718 | 93.76 | 3 | 93.14 | 67.96
136 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District | SM/07721 | 53.33 | 3 | 41.07 | 40.67
137 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P | SM/07772 | 295.16 | 5 | 194.13 | 194.13
138 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo | SM/07785 | 44.45 | 2 | 36.94 | 25.68
139 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagw | SM/07793 | 157.17 | 2 | 155.97 | 0
140 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - | SM/08190 | 1045.27 | 10 | 503.7 | 515.96
141 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- | SM/08195 | 480.62 | 17 | 399.5 | 129.34
142 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/08201 | 548.73 | 2 | 528.09 | 216.06
143 | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 | SM/08867 | 2776.84 | 27 | 2559.02 | 653.33
144 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under | SM/08274 | 384.16 | 11 | 245.02 | 231.94
145 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) | SM/08275 | 558.86 | 7 | 741.83 | 124.27
146 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshid | SM/08910 | 487.62 | 1 | 373.58 | 0
147 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad | SM/09741 | 11.7 | 1 | 2.58 | 0
148 | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ratanpur ( 313841 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Mursh | SM/09745 | 210.01 | 1 | 13.05 | 13.05
149 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh | SM/09844 | 9.41 | 3 | 13.07 | 3.97
150 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | 313.08 | 7 | 33.25 | 23.48
151 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | 953.7 | 10 | 1038.45 | 263.16
152 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | 607.53 | 9 | 328.98 | 52.98
153 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | 939.08 | 14 | 1086.47 | 447.6
154 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/08099 | 366.99 | 6 | 248.27 | 160.31
155 | Berhampur Division I | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | 300.98 | 4 | 248.89 | 46.66
156 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | 698.71 | 9 | 430.86 | 88.52
157 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | 442.96 | 9 | 221.77 | 54.67
158 | Berhampur Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | 33305.51 | 31 | 36716.03 | 9438.82
159 | Murshidabad Division | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | 852.84 | 6 | 687.95 | 78.25
160 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11791 | 698.06 | 9 | 423.76 | 295.66
161 | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | 946.46 | 12 | 546.69 | 43.31
162 | Murshidabad Division | PUNIA AND ADJOINING MOUJAS PWSS | SM/13933 | 714.78 | 7 | 629.1 | 145.23
163 | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS | SM/13934 | 917.51 | 9 | 758.55 | 1.86
164 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | 899.98 | 10 | 609.53 | 25.85
165 | Berhampur Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | 591.27 | 9 | 342.59 | 42.77
166 | Berhampur Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | 338.02 | 7 | 158.12 | 29.87
167 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | 759.79 | 8 | 563.77 | 2.79
168 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | 978.6 | 10 | 548.3 | 114.59
169 | Berhampur Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | 998.3 | 7 | 1003.25 | 2.9
170 | Berhampur Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | 995.8 | 7 | 641.98 | 98.56
171 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. | SM/15232 | 903.97 | 8 | 476.01 | 1.3
172 | Murshidabad Division | GHORAMARA PIPED WATER SUPPLY SCHEME. | SM/15049 | 704.88 | 5 | 359 | 5.31
173 | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | 758.85 | 9 | 337.93 | 0
174 | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | 558.72 | 8 | 509.41 | 116.22
175 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/16241 | 291.78 | 7 | 273.03 | 25.19
176 | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15836 | 762.57 | 8 | 715.45 | 97.3
177 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Mirzapur Ground water Based PWSS, Block-Raghunathganj-I , Dist- Murshidabad under MEDB, PHE Dte. | SM/15351 | 0 | 1 | 6.39 | 0
178 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | 820.5 | 10 | 532.51 | 0
179 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at FATELLAPUR Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. | SM/15340 | 0 | 0 | 0 | 0
180 | Berhampur Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME | SM/16018 | 396.07 | 7 | 143.6 | 7.05
181 | Murshidabad Division | GOPJAN(P) PIPED WATER SUPPLY SCHEME, BLOCK- BERHAMPORE , DISTRICT- MURSHIDABAD. | SM/16444 | 40.62 | 2 | 36.84 | 0
182 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. | SM/16543 | 543.46 | 7 | 386.29 | 6.59
183 | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16546 | 541.56 | 3 | 83.09 | 0
184 | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . | SM/16043 | 413.88 | 6 | 152.68 | 9.11
185 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16046 | 40.62 | 2 | 36.81 | 0
186 | Berhampur Division I | Mini piped water supply scheme (maximum 100 households) Village-Sonadiar Zone-I, Block-Berhampore, District- Murshidabad. | SM/16500 | 40.62 | 2 | 36.77 | 0
187 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Arazi Narayanpur, Block- Lalgola, District- Murshidabad. | SM/16502 | 38.62 | 2 | 35.2 | 0
188 | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. | SM/16175 | 765.79 | 10 | 481.28 | 87.49
189 | Murshidabad Division | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. | SM/16209 | 40.62 | 3 | 8.75 | 0
190 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas | SM/08279 | 340.16 | 11 | 367.64 | 204.98
191 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan (315979) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Buwan Block of Murshidabad District under Murshidabad Divisi | SM/09835 | 13.03 | 1 | 7.78 | 0
192 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II | SM/11198 | 592.03 | 8 | 495.27 | 2.24
193 | Murshidabad Division | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16416 | 541.33 | 3 | 423.68 | 0
194 | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | 692.82 | 7 | 427.1 | 0
195 | Murshidabad Division | Augmentation of Salar Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16423 | 540.61 | 5 | 513.4 | 0
196 | Berhampur M/E Division | Implementation of affordable IoT System at Habaspur water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15995 | 0 | 0 | 0 | 0
197 | Berhampur Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | 589.74 | 5 | 321.91 | 42.86
198 | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | 258.1 | 5 | 230.7 | 0
199 | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16565 | 803.55 | 7 | 532.91 | 0
200 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/16353 | 998.86 | 12 | 699.29 | 165.65
201 | Berhampur M/E Division | Implementation of affordable IoT System at RAMAKANTAPUR water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15730 | 0 | 0 | 0 | 0
202 | Berhampur M/E Division | Implementation of affordable IoT System at Kadoa water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15731 | 0 | 0 | 0 | 0
203 | Berhampur M/E Division | Implementation of affordable IoT System at Hilora Zone-I ,II & III water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15732 | 0 | 0 | 0 | 0
204 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15917 | 998.29 | 7 | 600.08 | 0
205 | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | 528.16 | 7 | 403.16 | 3.08
206 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | 801.92 | 7 | 278.45 | 73.85
207 | Berhampur M/E Division | Implementation of affordable IoT System at Giria Zone-I &II water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15711 | 0 | 0 | 0 | 0
208 | Berhampur Division I | MALIPUR PIPED WATER SUPPLY SCHEME. | SM/16785 | 421.98 | 6 | 169.12 | 12.85
209 | Berhampur M/E Division | Implementation of affordable IoT System at Madna Zone-I & II water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15671 | 0 | 0 | 0 | 0
210 | Berhampur M/E Division | Implementation of affordable IoT System at Hafania water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15727 | 0 | 0 | 0 | 0
211 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A | SM/08687 | 601.79 | 10 | 461.34 | 232.02
212 | Berhampur M/E Division | Implementation of affordable IoT System at Jadabpur Nimtala W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15686 | 0 | 0 | 0 | 0
213 | Berhampur M/E Division | Implementation of affordable IoT System at Salar water supply Scheme in Bharatpur-II Block, Dist- Murshidabad. | SM/15687 | 0 | 0 | 0 | 0
214 | Berhampur M/E Division | Implementation of affordable IoT System at Kusumgachhi water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15670 | 0 | 0 | 0 | 0
215 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | 778.66 | 6 | 78.68 | 3.23
216 | Berhampur M/E Division | Implementation of affordable IoT System at Basudebpur water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15676 | 0 | 0 | 0 | 0
217 | Berhampur M/E Division | Implementation of affordable IoT System at Keyadanga, Zone-I & II water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15683 | 0 | 0 | 0 | 0
218 | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS | SM/15941 | 698.09 | 8 | 483.83 | 45.01
219 | Berhampur M/E Division | Implementation of affordable IoT System at Jot Sundar water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15740 | 0 | 0 | 0 | 0
220 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16754 | 526.89 | 4 | 137.86 | 2.44
221 | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/16867 | 209.46 | 3 | 154.84 | 0
222 | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | 81.23 | 9 | 88.23 | 0.73
223 | Berhampur M/E Division | Implementation of affordable IoT System at Salamatpur water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15706 | 0 | 0 | 0 | 0
224 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme | SM/07229 | 18.59 | 2 | 17.9 | 13.34
225 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. | SM/18542 | 1898.34 | 7 | 1275.49 | 0
226 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. | SM/18364 | 1761.66 | 7 | 762.36 | 0
227 | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. | SM/19126 | 1098.41 | 7 | 593.15 | 10.99
228 | Murshidabad Division | Augmentation of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundabag GP Murshidabad District under Murshidabad Division PHE Dte . | SM/18393 | 1119.66 | 1 | 968.51 | 0
229 | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. | SM/18590 | 1563.27 | 5 | 896.91 | 0
230 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Ramchandrapur (Code-314219) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-B) | SM/07733 | 55.09 | 1 | 28.26 | 11.14
231 | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME | SM/16398 | 422.27 | 6 | 139.39 | 0
232 | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS | SM/18466 | 1476.45 | 12 | 1171.09 | 126.6
233 | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18830 | 1419.76 | 11 | 842.93 | 0
234 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | 995.02 | 9 | 623.22 | 10.78
235 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | SM/07512 | 66.82 | 3 | 110.4 | 43.57
236 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagharpur Ramna (314665) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-V) | SM/07671 | 138.2 | 1 | 10.04 | 10.04
237 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba | SM/07705 | 143.18 | 2 | 142.15 | 91.47
238 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C | SM/07724 | 99.92 | 2 | 84.66 | 50.6
239 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water | SM/07726 | 76.06 | 2 | 47.61 | 44.61
240 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Malipara Village (Code-314452), Saaragachi Village (Code-314453),Chainpara Village (Code-314457),Rameswarbati Village (Code-31445 | SM/07728 | 63.18 | 1 | 49.93 | 6.2
241 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 | SM/06978 | 90.08 | 7 | 75.62 | 63.91
242 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme | SM/06979 | 46.15 | 4 | 33.77 | 36.83
243 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri | SM/07278 | 88.35 | 9 | 90 | 50.01
244 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) | SM/07282 | 99.99 | 4 | 77.05 | 45.8
245 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) | SM/07732 | 118.61 | 1 | 95.85 | 36.54
246 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme | SM/06980 | 80.61 | 5 | 80.47 | 63.68
247 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) | SM/07230 | 74.26 | 2 | 73.26 | 46.21
248 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme | SM/07232 | 21.55 | 2 | 18.9 | 12.99
249 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs | SM/07686 | 200.91 | 3 | 86.29 | 86.29
250 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu | SM/07698 | 95.9 | 2 | 94.76 | 53.88
251 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist | SM/07288 | 99.99 | 4 | 83.59 | 17.04
252 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) | SM/07291 | 51.34 | 4 | 34.11 | 10.4
253 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric | SM/07292 | 63.73 | 6 | 161.58 | 41.44
254 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) | SM/07716 | 12.33 | 2 | 8.62 | 2.45
255 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram | SM/07682 | 131.02 | 10 | 106.57 | 61.17
256 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M | SM/07888 | 162.87 | 2 | 139.93 | 64.08
257 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 | SM/08192 | 349.63 | 13 | 208.99 | 113.75
258 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur | SM/08194 | 442.13 | 15 | 339.55 | 297.11
259 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08906 | 505.26 | 2 | 436.16 | 0
260 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa | SM/08282 | 497.66 | 18 | 431.23 | 153.51
261 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | 717.96 | 27 | 559.06 | 329.19
262 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | 870.99 | 9 | 793.79 | 419.51
263 | Berhampur Division I | Extension of pipe line from existing PWSS to different Anganwadi Centers (AWCs), located within the command area of PWSS. | SM/09026 | 0 | 1 | 485.97 | 328.6
264 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brahmanigram ( 314319 ) and Bergram ( 314328 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of | SM/09747 | 94.96 | 2 | 42.11 | 0
265 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B | SM/09750 | 265.85 | 3 | 79.56 | 2.38
266 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl | SM/09752 | 46.25 | 2 | 30.99 | 0
267 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba | SM/09758 | 76.56 | 3 | 83.15 | 35.15
268 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio | SM/11163 | 195.5 | 2 | 69.16 | 9.6
269 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D | SM/09840 | 29.12 | 5 | 43.43 | 23.5
270 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D | SM/09766 | 13.96 | 2 | 9.67 | 6.98
271 | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | 971.89 | 11 | 812.3 | 122.09
272 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10626 | 525.47 | 11 | 500.77 | 226.64
273 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | 354.9 | 7 | 284.09 | 19.69
274 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | 512.37 | 5 | 441.4 | 51.73
275 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur, (313919, 313910, 313912, 313920) of Madna under Ground water based water supply scheme for arsenic affected areas of Suti-I Block | SM/11217 | 288.41 | 2 | 49.94 | 0
276 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11562 | 836.5 | 9 | 435.15 | 78.2
277 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11566 | 939.3 | 9 | 519.4 | 30.19
278 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11570 | 943.42 | 8 | 478.34 | 206.41
279 | Murshidabad Division | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | 758.82 | 5 | 593.7 | 0
280 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | 102.8 | 6 | 56.11 | 29.01
281 | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | 605.27 | 9 | 530.66 | 92.57
282 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | 988.06 | 8 | 756.65 | 105.48
283 | Berhampur Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14951 | 557.12 | 5 | 328.74 | 2.56
284 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | 427.57 | 7 | 270.86 | 169.69
285 | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | 892.38 | 6 | 843.19 | 287.43
286 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE | SM/14629 | 680.05 | 4 | 300.07 | 178.5
287 | Berhampur Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . | SM/15227 | 804.99 | 8 | 535.26 | 0
288 | Berhampur Division I | Augmentation of Bali Zone-III pipe water supply scheme . | SM/15228 | 842.2 | 7 | 539.89 | 39.63
289 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KHAYRAMARI Part-B Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. | SM/15293 | 0 | 1 | 6.39 | 0
290 | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | 770.2 | 8 | 689.53 | 146.85
291 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . | SM/14737 | 808.29 | 7 | 457.4 | 31.6
292 | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | 492.25 | 7 | 406.67 | 0
293 | Murshidabad Division | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | 831.53 | 5 | 679.79 | 8.74
294 | Murshidabad Division | KUMAR SANDA AND ADJOINING MOUJAS PWSS | SM/14238 | 1000.77 | 3 | 748.32 | 0
295 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/16244 | 715.32 | 8 | 666.3 | 248.93
296 | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16245 | 657.87 | 6 | 430.26 | 0
297 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jorgacha Part-I, Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | SM/15350 | 0 | 1 | 6.44 | 0
298 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | 113.82 | 5 | 97.83 | 0
299 | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. | SM/15955 | 900.63 | 7 | 579.38 | 21.12
300 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAK CHANDPARA , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. | SM/16440 | 38.92 | 2 | 35.36 | 0
301 | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | 841.25 | 7 | 465.33 | 16.74
302 | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | 996.9 | 5 | 511.78 | 0.59
303 | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. | SM/16550 | 979.6 | 6 | 535.89 | 0
304 | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | 245.29 | 6 | 174.46 | 11.5
305 | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-B) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16554 | 302 | 1 | 337.24 | 73.73
306 | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME | SM/16555 | 789.76 | 6 | 431.62 | 2.83
307 | Berhampur M/E Division | Implementation of affordable IoT System at Rajarampur water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15987 | 0 | 0 | 0 | 0
308 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16455 | 779.3 | 8 | 603.37 | 186.79
309 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. | SM/15638 | 827.89 | 9 | 403.66 | 169.36
310 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. | SM/16177 | 662.59 | 6 | 341.38 | 7.17
311 | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/16178 | 800.76 | 5 | 400.89 | 0
312 | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | 453.71 | 8 | 348.98 | 44.53
313 | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | 785.06 | 9 | 564.92 | 1.91
314 | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | 541.33 | 5 | 466.21 | 10.69
315 | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. | SM/16417 | 709.24 | 9 | 512.18 | 18.03
316 | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. | SM/16216 | 497.21 | 9 | 346.08 | 9.95
317 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. | SM/16380 | 994.64 | 12 | 516.2 | 57.16
318 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | 578.91 | 6 | 315.54 | 2.39
319 | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | 615.3 | 9 | 586.7 | 62.31
320 | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | 710.31 | 7 | 707.46 | 74.83
321 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16560 | 492.65 | 6 | 226.67 | 0
322 | Berhampur M/E Division | Implementation of affordable IoT System at Bajegajipur water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15729 | 0 | 0 | 0 | 0
323 | Berhampur M/E Division | Implementation of affordable IoT System at Jagtai water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15737 | 0 | 0 | 0 | 0
324 | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | 245.5 | 10 | 206.41 | 6.73
325 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | 603 | 9 | 362.83 | 4.59
326 | Berhampur M/E Division | Implementation of affordable IoT System at Andhua W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15688 | 0 | 0 | 0 | 0
327 | Berhampur M/E Division | Implementation of affordable IoT System at Budharpara water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15710 | 0 | 0 | 0 | 0
328 | Berhampur M/E Division | Implementation of affordable IoT System at Andharmanik water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15712 | 0 | 0 | 0 | 0
329 | Berhampur Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | 711.04 | 5 | 376.31 | 59.32
330 | Berhampur M/E Division | Implementation of affordable IoT System at Dhusuripara water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15674 | 0 | 0 | 0 | 0
331 | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS | SM/15680 | 801.52 | 7 | 622.42 | 30.46
332 | Berhampur M/E Division | Implementation of affordable IoT System at Ahiran water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15684 | 0 | 0 | 0 | 0
333 | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | 203.08 | 8 | 177.75 | 4.75
334 | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS | SM/15678 | 813.42 | 7 | 651.09 | 0
335 | Berhampur M/E Division | Implementation of affordable IoT System at Ballalpur W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15692 | 0 | 0 | 0 | 0
336 | Murshidabad Division | MANDALSAR AND ADJOINING MOUJAS PWSS | SM/15938 | 479.13 | 5 | 424.04 | 49.69
337 | Berhampur M/E Division | Implementation of affordable IoT System at Bharatpur water supply Scheme in Bharatpur-I Block, Dist- Murshidabad. | SM/15700 | 0 | 0 | 0 | 0
338 | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16863 | 556.98 | 5 | 509.85 | 0
339 | Berhampur M/E Division | Implementation of affordable IoT System at Basabari water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15695 | 0 | 0 | 0 | 0
340 | Berhampur M/E Division | Implementation of affordable IoT System at Tenya Zone-I & II water supply Scheme in Bharatpur-II Block, Dist- Murshidabad. | SM/15698 | 0 | 0 | 0 | 0
341 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground | SM/07720 | 92.89 | 2 | 86.84 | 46.45
342 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/17850 | 469.54 | 8 | 296.38 | 9.08
343 | Berhampur Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | 1265.2 | 10 | 813.02 | 40.27
344 | Murshidabad Division | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. | SM/18413 | 1029.02 | 4 | 769.15 | 0
345 | Berhampur Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | 1356.19 | 12 | 903.77 | 14.74
346 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. | SM/19125 | 1124.55 | 5 | 603.57 | 0
347 | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/18689 | 2084.84 | 8 | 1034.41 | 17.41
348 | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS | SM/18452 | 1267.95 | 7 | 1129.9 | 125.46
349 | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD | SM/18896 | 16379.52 | 8 | 12042.79 | 0
350 | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A | SM/18767 | 980.49 | 57 | 889.87 | 15.49
351 | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. | SM/18737 | 1052.46 | 7 | 878.45 | 40.73
352 | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS | SM/18464 | 1754.46 | 7 | 1511.53 | 42.63
353 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18662 | 2059.61 | 5 | 867.05 | 2.11
354 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/18831 | 2130.14 | 13 | 1449.4 | 10.46
355 | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/18755 | 1126.44 | 6 | 602.6 | 6.98
356 | Berhampur Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | 1478.49 | 12 | 976.68 | 185.2
357 | Berhampur Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | 1060.31 | 10 | 694.58 | 2.81
358 | Berhampur Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | 38369 | 29 | 31892.47 | 846.42
359 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. | SM/18702 | 1288.62 | 7 | 660.95 | 0
360 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) | SM/07910 | 38.44 | 10 | 38.54 | 19.84
361 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Sahebnagar (VillageCode-314609) under command area of Kazipara ground water supply scheme (Part-A) | SM/07222 | 66.28 | 1 | 61.97 | 0
362 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) | SM/07922 | 105.77 | 4 | 119.81 | 47.27
363 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) | SM/07511 | 62.34 | 4 | 90.82 | 32.52
364 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) | SM/06983 | 93.43 | 2 | 93.43 | 29.1
365 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida | SM/08100 | 420.14 | 4 | 172.38 | 0
366 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08115 | 552.45 | 7 | 405.3 | 305.11
367 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code | SM/06977 | 99.54 | 5 | 90.03 | 79.84
368 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) | SM/07729 | 64.96 | 2 | 55.66 | 32.48
369 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) | SM/07731 | 94.33 | 2 | 93.71 | 32.65
370 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid | SM/07284 | 74.76 | 5 | 123.68 | 12.77
371 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P | SM/07697 | 168.17 | 2 | 166.57 | 57.28
372 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) | SM/07908 | 63.81 | 4 | 152.51 | 42.23
373 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) | SM/07767 | 285.68 | 6 | 249.83 | 37.24
374 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of | SM/07674 | 295.52 | 13 | 297.51 | 210.09
375 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) | SM/07675 | 173.36 | 2 | 175.09 | 0.87
376 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply | SM/07794 | 82.35 | 2 | 81.68 | 7.37
377 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) | SM/07719 | 85.64 | 3 | 84.96 | 13.63
378 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gobindotala Village (Code-314454), Paschim Rampur (Code-314455) In The Command Area Of Paschim Rampur Ground Water Supply Scheme | SM/07783 | 88.5 | 1 | 66.78 | 22.53
379 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block | SM/07787 | 76.68 | 2 | 80.02 | 38.34
380 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc | SM/07789 | 115.48 | 1 | 78.84 | 21.1
381 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Taraf Rasulpur (314679) of P.T. Rasulpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/08186 | 357.84 | 1 | 7.3 | 0
382 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari (314589) of Katlamari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District (PART-I) | SM/08188 | 578.36 | 1 | 0 | 0
383 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) | SM/08200 | 380.89 | 8 | 336.19 | 141.86
384 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/08272 | 385.47 | 4 | 143.8 | 133.19
385 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08915 | 983.07 | 8 | 674.16 | 354.71
386 | Berhampur Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF | SM/08918 | 229.8 | 2 | 136.63 | 117.5
387 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Pakamati Mahula ( 315353 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under | SM/09740 | 9.7 | 1 | 4.16 | 4.16
388 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | SM/09746 | 328.18 | 4 | 239.94 | 7.88
389 | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | 835.07 | 14 | 140.57 | 101.35
390 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | SM/09749 | 81.3 | 2 | 61.42 | 34.05
391 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc | SM/09751 | 71.75 | 3 | 142.44 | 18.38
392 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kolan Radhakantapur (314523) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis | SM/09754 | 94.97 | 1 | 31.97 | 31.97
393 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | SM/09757 | 86.3 | 3 | 56.99 | 9.99
394 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di | SM/09837 | 34.02 | 3 | 56.53 | 15.9
395 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | 567.92 | 5 | 555.07 | 333.81
396 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10611 | 738.67 | 5 | 738.86 | 79.86
397 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Srikrishnapur ( 314737 ) of Aminabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshid | SM/09846 | 67.42 | 1 | 38.99 | 19.49
398 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under | SM/09851 | 28.53 | 2 | 9 | 9
399 | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | 962.13 | 14 | 904.21 | 349.65
400 | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | 640.21 | 10 | 562.96 | 338.85
401 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | 620.12 | 10 | 356.78 | 205.91
402 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo | SM/07790 | 89.83 | 2 | 89.28 | 44.92
403 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | 902.24 | 10 | 672.01 | 99.33
404 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11563 | 993.35 | 8 | 448.35 | 13.54
405 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | 786.26 | 8 | 409 | 174.04
406 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11567 | 723.92 | 7 | 433.65 | 28.5
407 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | 936.21 | 14 | 755.21 | 314.46
408 | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | 963.23 | 6 | 817.1 | 291.51
409 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ | SM/11229 | 568.17 | 4 | 353.15 | 5.94
410 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Jamna (315232) of Mahalandi Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Kandi Block of Murshidabad District Under Murshidabad Division PheDte. | SM/11233 | 222.96 | 2 | 31.27 | 0
411 | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. | SM/11234 | 159.1 | 3 | 60.68 | 37.78
412 | Murshidabad Division | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | 695.52 | 6 | 629.81 | 195.21
413 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of | SM/07280 | 97.62 | 3 | 29.29 | 29.29
414 | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | 927.78 | 11 | 856.49 | 236.08
415 | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | 655.64 | 7 | 429.47 | 106.53
416 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad | SM/07662 | 170.09 | 17 | 154.59 | 150.11
417 | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | 669.58 | 8 | 625.76 | 51.02
418 | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | 440.16 | 7 | 384.57 | 78.7
419 | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | 467.74 | 6 | 455.44 | 64.8
420 | Berhampur Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14433 | 838.18 | 10 | 553.51 | 31.14
421 | Berhampur Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14434 | 770.8 | 11 | 557.46 | 18.09
422 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | 621.73 | 4 | 230.17 | 0
423 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | 390.02 | 10 | 355.99 | 51.82
424 | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | 638.6 | 7 | 558.97 | 173.06
425 | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | 820.33 | 5 | 483.08 | 273.75
426 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. | SM/14631 | 488.47 | 6 | 284.78 | 0
427 | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | 674.05 | 10 | 576.66 | 38.98
428 | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | 569.98 | 13 | 540.24 | 46.32
429 | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | 277.07 | 6 | 281.67 | 36.78
430 | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16243 | 660.65 | 6 | 323.57 | 19.58
431 | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. | SM/15837 | 408.6 | 2 | 366.9 | 41.23
432 | Berhampur Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme | SM/16263 | 724.68 | 8 | 451.74 | 62.61
433 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. | SM/16435 | 33.9 | 2 | 30.95 | 0
434 | Berhampur M/E Division | Implementation of affordable IoT System at water supply Scheme in Bajupur-Madhupur (Zone-I&II) Block, Dist- Murshidabad. | SM/16010 | 0 | 0 | 0 | 0
435 | Berhampur M/E Division | Implementation of affordable IoT System at Kantanagar water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15985 | 0 | 0 | 0 | 0
436 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. | SM/16441 | 38.14 | 2 | 34.85 | 0
437 | Murshidabad Division | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | 641.21 | 6 | 525.68 | 1.8
438 | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | 813.92 | 7 | 438.06 | 1.74
439 | Berhampur M/E Division | Implementation of affordable IoT System at Maya water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15993 | 0 | 0 | 0 | 0
440 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-I, Block- Berhampore, District- Murshidabad. | SM/16044 | 40.62 | 2 | 36.8 | 0
441 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. | SM/16050 | 37.34 | 2 | 33.92 | 0
442 | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. | SM/16481 | 938.46 | 8 | 552.41 | 0
443 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | 681.2 | 6 | 413.03 | 0
444 | Murshidabad Division | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16172 | 471.99 | 8 | 409.28 | 0
445 | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16173 | 471.99 | 6 | 424.12 | 0
446 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15919 | 780.33 | 5 | 430.33 | 39.76
447 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. | SM/16210 | 40.62 | 2 | 36.53 | 0
448 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Lahari, Block- Bhagwangola-II, District- Murshidabad. | SM/16213 | 40.62 | 2 | 36.8 | 0
449 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di | SM/07919 | 235.36 | 6 | 229.09 | 168.9
450 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE | SM/10013 | 274.1 | 8 | 170.06 | 12.1
451 | Berhampur Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16376 | 666.66 | 9 | 528.88 | 0
452 | Berhampur M/E Division | Implementation of affordable IoT System at Siteshnagar water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15983 | 0 | 0 | 0 | 0
453 | Berhampur M/E Division | Implementation of affordable IoT System at Hazi Mahhamadpur water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15991 | 0 | 0 | 0 | 0
454 | Berhampur M/E Division | IImplementation of affordable IoT System at Dakhin Hanumantanagar water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15994 | 0 | 0 | 0 | 0
455 | Berhampur Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | 415.43 | 5 | 146.89 | 6.63
456 | Berhampur M/E Division | Implementation of affordable IoT System at Jhikra water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16000 | 0 | 0 | 0 | 0
457 | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | 927.36 | 6 | 630.3 | 0
458 | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | 828.77 | 8 | 761.86 | 133.43
459 | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | 254.4 | 4 | 225.04 | 8.53
460 | Murshidabad Division | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15728 | 534.48 | 4 | 465.97 | 0
461 | Berhampur M/E Division | Implementation of affordable IoT System at Hasimpur water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15664 | 0 | 0 | 0 | 0
462 | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/16621 | 842.44 | 8 | 463.2 | 10.37
463 | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16111 | 124.95 | 7 | 108.77 | 3.94
464 | Berhampur Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS | SM/16789 | 390.77 | 7 | 157.92 | 0
465 | Berhampur M/E Division | Implementation of affordable IoT System at Sikdarpur water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15656 | 0 | 0 | 0 | 0
466 | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. | SM/15747 | 534.48 | 4 | 497.33 | 0
467 | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/15750 | 697.42 | 5 | 449.72 | 0
468 | Berhampur M/E Division | Implementation of affordable IoT System at Mahadeb nagar,Zone-I&II W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15685 | 0 | 0 | 0 | 0
469 | Berhampur M/E Division | Implementation of affordable IoT System at Sungai water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15716 | 0 | 0 | 0 | 0
470 | Berhampur M/E Division | Implementation of affordable IoT System at Kasiadanga Zone-I &II water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15720 | 0 | 0 | 0 | 0
471 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | 373.08 | 6 | 210.41 | 31.9
472 | Berhampur Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS | SM/16780 | 991.57 | 6 | 606.65 | 0
473 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16986 | 733.3 | 4 | 555.38 | 1.59
474 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VIII & XII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16989 | 999.61 | 1 | 487.03 | 0
475 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16990 | 928.12 | 2 | 621.17 | 0
476 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp | SM/07703 | 65.9 | 1 | 35.66 | 28
477 | Berhampur Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | 1544.31 | 16 | 1191.69 | 4.02
478 | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, | SM/18775 | 1549.76 | 8 | 995.92 | 34.47
479 | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . | SM/19123 | 1029.17 | 3 | 425.33 | 0
480 | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. | SM/19124 | 3659.55 | 8 | 1886.66 | 5.67
481 | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | 1936.25 | 12 | 1167.71 | 12.12
482 | Murshidabad Division | CHACHANDA PIPED WATER SUPPLY SCHEME. | SM/18382 | 1131.75 | 5 | 642.32 | 0
483 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18515 | 3298.88 | 7 | 1560.08 | 0
484 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P | SM/07906 | 291.34 | 2 | 182.05 | 145.67
485 | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/19111 | 1111.29 | 7 | 572.15 | 4.03
486 | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. | SM/18687 | 1027.21 | 6 | 518.72 | 0
487 | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. | SM/18692 | 1499.1 | 9 | 809.61 | 119.97
488 | Berhampur Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | 1196.31 | 8 | 729.18 | 146.57
489 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. | SM/18703 | 2237.11 | 14 | 682.24 | 2.23
490 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) | SM/07700 | 164.71 | 3 | 162.26 | 0
491 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( | SM/07913 | 96.61 | 3 | 62.18 | 18.1
492 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme | SM/07223 | 59.03 | 2 | 58.66 | 34.35
493 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme | SM/07225 | 30.52 | 2 | 30.32 | 16.81
494 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) | SM/07927 | 48 | 2 | 30.01 | 24
495 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bilaspur (314681) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) | SM/07516 | 79.12 | 1 | 3.46 | 3.46
496 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block | SM/07677 | 248.75 | 9 | 194.29 | 128.5
497 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh | SM/07679 | 122.92 | 2 | 86.98 | 86.98
498 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) | SM/07693 | 131.51 | 2 | 113.95 | 65.76
499 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) | SM/06973 | 50.08 | 3 | 46.66 | 40.07
500 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme | SM/06982 | 71.77 | 6 | 68.24 | 53.57
501 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | SM/07274 | 85.16 | 8 | 89.8 | 61.96
502 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par | SM/07275 | 21.9 | 5 | 18.97 | 11.68
503 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Naopukuria (Zone-K) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/07702 | 240.81 | 1 | 179.66 | 0
504 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) | SM/07727 | 49.3 | 2 | 48.82 | 17.12
505 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sundarpur (Code-314445) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-B) | SM/07730 | 68.76 | 1 | 53.12 | 16.75
506 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV | SM/07283 | 52.54 | 5 | 58.56 | 13.44
507 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B | SM/07287 | 72.14 | 8 | 58.71 | 27.36
508 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid | SM/07294 | 95.06 | 8 | 119.06 | 45.56
509 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur | SM/07684 | 112.77 | 3 | 98.03 | 43.73
510 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni | SM/07663 | 121.53 | 9 | 149.51 | 28.37
511 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07665 | 197.42 | 0 | 0 | 0
512 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat | SM/07666 | 299.57 | 17 | 88.14 | 36.45
513 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh | SM/07510 | 97.32 | 13 | 93.88 | 77.44
514 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) | SM/07768 | 281.95 | 5 | 153.19 | 140.94
515 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) | SM/07770 | 162.06 | 15 | 264.18 | 135.09
516 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs | SM/07773 | 139.17 | 6 | 144.08 | 77.48
517 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part | SM/07889 | 49.64 | 2 | 48.95 | 0
518 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa | SM/08187 | 489.6 | 13 | 172.25 | 120.96
519 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri | SM/08198 | 348.01 | 7 | 405.58 | 128.74
520 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08903 | 362.25 | 3 | 359.59 | 244.27
521 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/08907 | 674.11 | 2 | 561.36 | 0
522 | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M | SM/09742 | 191.97 | 5 | 192.84 | 33.44
523 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bamuha (313962) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad D | SM/09759 | 64.56 | 1 | 47.88 | 0
524 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | SM/09838 | 25.62 | 14 | 19.61 | 10.38
525 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh | SM/09839 | 17.46 | 2 | 24.7 | 5.74
526 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09768 | 60.39 | 3 | 42.98 | 0
527 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida | SM/09849 | 44.53 | 2 | 24.76 | 21.64
528 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Santoshpur (314329) &Chandanbati ( 314330 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of M | SM/09850 | 91.63 | 1 | 36.58 | 0
529 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | 774.74 | 18 | 586.07 | 121.24
530 | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | 694.67 | 5 | 431.93 | 66.68
531 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD | SM/10812 | 705.89 | 5 | 124.28 | 7.1
532 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11197 | 595.94 | 3 | 272.74 | 75.51
533 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Nimtita (313863) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District under Murshidabad Division PheDte. | SM/11215 | 164.09 | 2 | 45.09 | 24.27
534 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11564 | 949.24 | 14 | 814.12 | 118.97
535 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | 995.43 | 12 | 683.43 | 84.06
536 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | 514.74 | 8 | 284 | 95.64
537 | Berhampur Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | 937.92 | 10 | 736.73 | 76.37
538 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi | SM/11232 | 128.48 | 3 | 44.06 | 20.68
539 | Murshidabad Division | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | 690.38 | 5 | 562.37 | 160.06
540 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08112 | 777.42 | 12 | 712.56 | 443.59
541 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | 713.71 | 6 | 313.39 | 57.99
542 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand | SM/08191 | 333.13 | 6 | 259.72 | 64.82
543 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | 360.07 | 6 | 118.48 | 31.78
544 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | 499.1 | 10 | 385.92 | 32.55
545 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14833 | 474.11 | 10 | 207.73 | 19.24
546 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. | SM/13114 | 1270.06 | 2 | 483.58 | 0
547 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | 507.83 | 7 | 258.99 | 84.79
548 | Berhampur Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I | SM/15233 | 980.83 | 11 | 786.3 | 144.04
549 | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS | SM/15265 | 206.5 | 7 | 200.53 | 58.29
550 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Saktipur (ZONE- I ) Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15294 | 0 | 1 | 6.44 | 0
551 | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS | SM/15054 | 593 | 7 | 468.06 | 70.93
552 | Murshidabad Division | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. | SM/15064 | 997.95 | 5 | 496.11 | 47.08
553 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | 865.34 | 17 | 689.59 | 388.14
554 | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . | SM/16242 | 500.75 | 6 | 333.64 | 0
555 | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/15839 | 599.09 | 11 | 442.41 | 10.46
556 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) | SM/07926 | 38.41 | 4 | 59.82 | 18.09
557 | Berhampur Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . | SM/15518 | 436.62 | 9 | 303.95 | 109.86
558 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Ramkantapur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. | SM/15342 | 0 | 0 | 0 | 0
559 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dogachhi Zone - I Ground water Based PWSS, Block-Samserganj , Dist- Murshidabad under MEDB, PHE Dte. | SM/15344 | 0 | 1 | 6.39 | 0
560 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at MALIBARI Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15347 | 0 | 1 | 6.39 | 0
561 | Berhampur M/E Division | Implementation of affordable IoT System at Sekaendra water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15714 | 0 | 0 | 0 | 0
562 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-I, Block- Berhampore, District- Murshidabad. | SM/16432 | 40.62 | 2 | 36.81 | 0
563 | Berhampur M/E Division | Implementation of affordable IoT System at Dakhin Sahar water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16009 | 0 | 0 | 0 | 0
564 | Berhampur M/E Division | Implementation of affordable IoT System at Bhundarkismat water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/16011 | 0 | 0 | 0 | 0
565 | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | 121.85 | 6 | 110.82 | 4.6
566 | Berhampur M/E Division | Implementation of affordable IoT System at Hasanpur water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16003 | 0 | 0 | 0 | 0
567 | Berhampur Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | 758.25 | 9 | 470.13 | 25.52
568 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Chhalimpur, Block- Murshidabad Jiaganj, District- Murshidabad. | SM/16048 | 31.8 | 2 | 29.12 | 0
569 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. | SM/16049 | 40.62 | 2 | 36.35 | 0
570 | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | 898.14 | 7 | 538.64 | 0
571 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-I, Block- Nawda, District- Murshidabad. | SM/16499 | 40.62 | 2 | 36.83 | 0
572 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | 951.83 | 6 | 561.46 | 10.24
573 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15920 | 610.97 | 8 | 344.87 | 3.16
574 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15923 | 633 | 6 | 305.32 | 0
575 | Murshidabad Division | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16214 | 81.23 | 3 | 67.4 | 0
576 | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16420 | 890.75 | 9 | 439.91 | 10.5
577 | Berhampur M/E Division | Implementation of affordable IoT System at Telia water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15982 | 0 | 0 | 0 | 0
578 | Murshidabad Division | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | 436.24 | 4 | 377.92 | 3.19
579 | Murshidabad Division | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | 246.58 | 4 | 216.24 | 0
580 | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. | SM/15734 | 709.71 | 16 | 486.92 | 10.84
581 | Berhampur M/E Division | Implementation of affordable IoT System at AURANGABAD water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15665 | 0 | 0 | 0 | 0
582 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | 606.43 | 6 | 241.21 | 1.84
583 | Berhampur Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS | SM/16787 | 562.54 | 7 | 312.51 | 40.89
584 | Berhampur M/E Division | Implementation of affordable IoT System at Kankhuriya-Zafrabad water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15658 | 0 | 0 | 0 | 0
585 | Berhampur M/E Division | Implementation of affordable IoT System at Dogachi,Zone-I&IIwater supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15672 | 0 | 0 | 0 | 0
586 | Berhampur M/E Division | Implementation of affordable IoT System at Bhasaipaikar, Zone-I,II&III water supply Scheme in Shamsherganj Block, Dist- Murshidabad. | SM/15673 | 0 | 0 | 0 | 0
587 | Berhampur M/E Division | Implementation of affordable IoT System at Arjunpur W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15689 | 0 | 0 | 0 | 0
588 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16768 | 792.83 | 7 | 475.23 | 1.74
589 | Murshidabad Division | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS | SM/15942 | 540.51 | 6 | 471.01 | 200.05
590 | Berhampur M/E Division | Implementation of affordable IoT System at Harua water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15733 | 0 | 0 | 0 | 0
591 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | 852.05 | 12 | 535.33 | 30.52
592 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16988 | 934.56 | 2 | 579.18 | 0
593 | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | 549.36 | 6 | 418.61 | 5.84
594 | Berhampur M/E Division | Implementation of affordable IoT System at Bara Satui water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15696 | 0 | 0 | 0 | 0
595 | Berhampur M/E Division | Implementation of affordable IoT System at Diar Shyampur (Zone-I &II) water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/18187 | 0 | 0 | 0 | 0
596 | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS | SM/18312 | 1223.05 | 6 | 918.56 | 0
597 | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS | SM/18324 | 1442.05 | 8 | 1272.44 | 1.91
598 | Berhampur Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | 1596.9 | 10 | 999.52 | 46.99
599 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F | SM/08113 | 746.48 | 10 | 598.52 | 274.22
600 | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/18663 | 2018.37 | 9 | 1651.77 | 205.87
601 | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS | SM/18453 | 1240.43 | 11 | 1125.27 | 59.04
602 | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS | SM/18454 | 1083.25 | 8 | 877.39 | 35.93
603 | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. | SM/18693 | 1754.34 | 11 | 1268.59 | 3.09
604 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . | SM/14736 | 677.36 | 11 | 591.71 | 63.57
605 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | 1074.75 | 13 | 752.21 | 194.42
606 | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. | SM/18700 | 3550.58 | 11 | 1502.85 | 73.73
607 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II | SM/07915 | 98.09 | 2 | 65.22 | 65.22
608 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- | SM/07921 | 91.1 | 2 | 63.01 | 63.01
609 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis | SM/07925 | 69.2 | 7 | 31.28 | 9.42
610 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sekhalipara (314580) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07517 | 77.39 | 1 | 100.17 | 11.39
611 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) | SM/07687 | 99.51 | 2 | 98.47 | 49.76
612 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr | SM/07691 | 84.54 | 5 | 46.83 | 44.51
613 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District | SM/07692 | 283.13 | 4 | 281.31 | 197.61
614 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme | SM/06984 | 99.87 | 4 | 93.8 | 38.64
615 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/07701 | 169.75 | 2 | 167.8 | 0
616 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08114 | 312.34 | 4 | 308.14 | 12.7
617 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- | SM/07907 | 263.57 | 9 | 343.25 | 198.62
618 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II | SM/07683 | 158.56 | 4 | 156.48 | 31.16
619 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi | SM/07506 | 83.51 | 11 | 125.88 | 67.16
620 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) | SM/07769 | 173.5 | 9 | 196.89 | 141.85
621 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag | SM/07694 | 83.34 | 2 | 82.71 | 37.16
622 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) | SM/07723 | 89.7 | 2 | 88.52 | 44.85
623 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) | SM/07771 | 113.58 | 10 | 101.69 | 11.97
624 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola | SM/07791 | 63.22 | 2 | 57.1 | 43.32
625 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu | SM/08899 | 373.6 | 3 | 328.41 | 206.51
626 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P | SM/08901 | 310.52 | 4 | 276.33 | 211.95
627 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj | SM/08197 | 521.6 | 9 | 358.47 | 348.88
628 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme | SM/08276 | 342.72 | 4 | 192.87 | 170.36
629 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/08280 | 305.04 | 6 | 131.25 | 93.21
630 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | 995.85 | 14 | 813.8 | 434.66
631 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | 96.99 | 7 | 103.87 | 54.94
632 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis | SM/09760 | 66.1 | 2 | 43.73 | 33.05
633 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad | SM/09761 | 43.78 | 3 | 31.4 | 4.17
634 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di | SM/09847 | 67.61 | 2 | 57.7 | 13.15
635 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II | SM/07669 | 151.27 | 3 | 311.07 | 27.38
636 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do | SM/07289 | 78.74 | 4 | 46.74 | 21.34
637 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | 244.68 | 4 | 169.51 | 30.61
638 | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | 998.51 | 11 | 537.46 | 22.28
639 | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/11716 | 174.5 | 5 | 63.47 | 17.78
640 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | 582.29 | 7 | 289.38 | 25.85
641 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | 851.94 | 10 | 702.49 | 24.13
642 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | 671.73 | 9 | 467.63 | 17.02
643 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II | SM/10797 | 762.78 | 4 | 627.95 | 0
644 | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | 361.5 | 5 | 270.2 | 49.21
645 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | 553.93 | 9 | 484.74 | 43.08
646 | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | 635.19 | 9 | 583.26 | 89.43
647 | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | 337.8 | 7 | 310.37 | 9.26
648 | Murshidabad Division | SERPUR AND ADJOINING MOUJAS PWSS | SM/13930 | 764.95 | 5 | 612.31 | 5.05
649 | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | 389.65 | 7 | 332.54 | 5.89
650 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | 833.08 | 7 | 505.01 | 196.19
651 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | 202.23 | 7 | 111.54 | 18.48
652 | Berhampur Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | 982.3 | 11 | 671.65 | 10.02
653 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | 628.88 | 6 | 270.04 | 2.56
654 | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | 864.73 | 6 | 718.7 | 130.08
655 | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | 843.11 | 9 | 864.16 | 304.93
656 | Berhampur Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. | SM/15519 | 969.51 | 8 | 705.03 | 20.08
657 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. | SM/14735 | 915.51 | 12 | 452.87 | 18.07
658 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . | SM/14739 | 244.16 | 8 | 167.79 | 31.63
659 | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. | SM/15067 | 959.55 | 9 | 803.41 | 13.46
660 | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | 998.83 | 6 | 811.31 | 0
661 | Berhampur Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16266 | 904.77 | 9 | 551.53 | 65.71
662 | Murshidabad Division | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | 842.7 | 7 | 657.46 | 5.57
663 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KARIMPUR JALANGI Zone-I Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. | SM/15353 | 0 | 1 | 6.39 | 0
664 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JITPUR (ZONE II) Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | SM/15354 | 0 | 1 | 6.43 | 0
665 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dhulauri Part-I Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | SM/15355 | 0 | 1 | 6.44 | 0
666 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply | SM/06974 | 91.48 | 4 | 86.8 | 76.08
667 | Murshidabad Division | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16239 | 820.76 | 5 | 513.68 | 0
668 | Berhampur M/E Division | Implementation of affordable IoT System at Putia water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15713 | 0 | 0 | 0 | 0
669 | Berhampur M/E Division | Implementation of affordable IoT System at Digha water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/16007 | 0 | 0 | 0 | 0
670 | Berhampur Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE ¿ BILGOBRA , BLOCK- BHAGAWANGOLA-I, DISTRICT MURSHIDABAD. | SM/16439 | 36.06 | 1 | 26.73 | 0
671 | Berhampur M/E Division | Implementation of affordable IoT System at Makimnagar water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15989 | 0 | 0 | 0 | 0
672 | Berhampur Division I | Mini piped water supply scheme (maximum 100 households) Village-Sona Diar Zone-II, Block-Berhampore, District- Murshidabad. | SM/16047 | 35.93 | 2 | 32.82 | 0
673 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16405 | 907.34 | 6 | 606.93 | 4.06
674 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16407 | 969.05 | 8 | 580.6 | 0
675 | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16170 | 471.99 | 9 | 382.78 | 25.17
676 | Berhampur M/E Division | Implementation of affordable IoT System at Sahajadpur,Zone-I &II water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15709 | 0 | 0 | 0 | 0
677 | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | 252.27 | 7 | 229.22 | 65.53
678 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Kuchidanga, Block- Lalgola, District- Murshidabad. | SM/16503 | 31.65 | 2 | 28.85 | 0
679 | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15916 | 982.94 | 3 | 818.26 | 155.56
680 | Murshidabad Division | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. | SM/16413 | 720.5 | 7 | 428.01 | 65.63
681 | Berhampur M/E Division | Implementation of affordable IoT System at Nasipur water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15997 | 0 | 0 | 0 | 0
682 | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | 242.17 | 6 | 170.11 | 4.92
683 | Berhampur M/E Division | Implementation of affordable IoT System at Ghorapakhiagangin Zone-I & II water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15736 | 0 | 0 | 0 | 0
684 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15918 | 518.94 | 6 | 107.49 | 0
685 | Murshidabad Division | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. | SM/15741 | 636.25 | 5 | 627.38 | 2.04
686 | Berhampur Division I | GOBINDAPUR PWSS | SM/16784 | 422.85 | 11 | 335.05 | 39.14
687 | Murshidabad Division | BADUA AND IT'S ADJOINING MOUJAS | SM/15682 | 736.24 | 3 | 612.68 | 0
688 | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS | SM/15690 | 427.3 | 7 | 382.23 | 7.37
689 | Berhampur M/E Division | Implementation of affordable IoT System at Bewa,Zone-II W/S Scheme water supply Scheme in Farakka Block, Dist- Murshidabad. | SM/15693 | 0 | 0 | 0 | 0
690 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-III, Block- Berhampore, District- Murshidabad. | SM/16812 | 34.04 | 2 | 31.1 | 0
691 | Murshidabad Division | ALAMPUR AND ADJOINING MOPUJAS PWSS | SM/16813 | 444.78 | 6 | 310.74 | 4.07
692 | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. | SM/15943 | 849.64 | 9 | 492.22 | 16.14
693 | Berhampur M/E Division | Implementation of affordable IoT System at Fatellapur water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15738 | 0 | 0 | 0 | 0
694 | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | 981.89 | 8 | 851.31 | 0
695 | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | 575.4 | 7 | 326.39 | 1.52
696 | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. | SM/16864 | 863.66 | 8 | 520.67 | 6.32
697 | Berhampur Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | 613.13 | 8 | 365.44 | 51.68
698 | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. | SM/18185 | 613.23 | 9 | 278.45 | 2.11
699 | Berhampur Division I | HABASPUR AND ADJOINING MOUJAS PWSS | SM/18238 | 1547.96 | 0 | 0 | 0
700 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. | SM/18543 | 1120.71 | 9 | 266.31 | 0
701 | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS | SM/18396 | 1115.39 | 10 | 996.23 | 37.7
702 | Murshidabad Division | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/18777 | 1121.12 | 12 | 958 | 63.46
703 | Murshidabad Division | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18471 | 1118.46 | 4 | 525.82 | 0
704 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI | SM/19017 | 102.66 | 3 | 102.48 | 4.48
705 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. | SM/19018 | 187.45 | 5 | 178.77 | 0
706 | Murshidabad Division | Source Augumentation& Functional Household Tap Connections (FHTC) of Mouza Radhakrishanapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148, 314149, 314150, 314151, 314153 ) of Lalgola Under Ground Water Based Water Supply Scheme For Arse | SM/19019 | 872.83 | 2 | 52.16 | 0
707 | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. | SM/18556 | 1383.64 | 7 | 796.02 | 0
708 | Murshidabad Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. | SM/18982 | 220.24 | 2 | 101.17 | 0
709 | Berhampur Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | 1865.49 | 7 | 1108.71 | 24.07
710 | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/18688 | 1068.33 | 14 | 880.76 | 89.77
711 | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18773 | 994.52 | 5 | 766.52 | 2.12
712 | Berhampur Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | 4390.37 | 8 | 3569.49 | 179.77
713 | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. | SM/18701 | 1931.29 | 6 | 1599.89 | 71.32
714 | Berhampur Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | 1472.99 | 13 | 1146.72 | 52.31
715 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07911 | 167.77 | 2 | 131.03 | 0
716 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II | SM/07920 | 95.93 | 2 | 79.79 | 34.42
717 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) | SM/07672 | 161.68 | 7 | 170.62 | 81.63
718 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/07704 | 64.01 | 1 | 43.31 | 0
719 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) | SM/07276 | 95.4 | 6 | 145.86 | 33.47
720 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi | SM/07281 | 99.11 | 5 | 72.85 | 3.18
721 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme | SM/07228 | 84.17 | 4 | 79.97 | 44.98
722 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme | SM/07231 | 71.2 | 2 | 71.98 | 20.81
723 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme | SM/07233 | 97.22 | 2 | 96.28 | 48.61
724 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o | SM/07235 | 81.52 | 4 | 80.48 | 61.37
725 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | 58.14 | 4 | 58 | 39.68
726 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | SM/07909 | 114.54 | 3 | 80 | 43.3
727 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe | SM/07667 | 241.98 | 15 | 155.8 | 100.47
728 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P | SM/07715 | 69.44 | 3 | 57.99 | 41.97
729 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi | SM/07774 | 205.5 | 3 | 222.87 | 124.88
730 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-II) | SM/07681 | 290.84 | 1 | 63.06 | 63.06
731 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) | SM/07792 | 94.73 | 2 | 78.44 | 39.69
732 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A | SM/08184 | 376.23 | 10 | 264.77 | 129.65
733 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | 385.71 | 4 | 296.9 | 157.6
734 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid | SM/08273 | 665.47 | 9 | 603.65 | 153.54
735 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08909 | 460.21 | 1 | 350.09 | 0
736 | Berhampur Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | 183.43 | 5 | 126.07 | 64.8
737 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan | SM/09737 | 875.99 | 5 | 647.6 | 78.22
738 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | 1037.9 | 8 | 486.7 | 49.6
739 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block | SM/09753 | 389.19 | 6 | 274.15 | 168.26
740 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Batkamari ( 314689 ) of Jorgachha under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad | SM/09842 | 34.36 | 1 | 22.28 | 16
741 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | 184.33 | 11 | 139.78 | 113.27
742 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D | SM/09848 | 34.24 | 2 | 20.73 | 20.41
743 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | 567.12 | 8 | 205.86 | 67.08
744 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | 579.64 | 7 | 308.4 | 136.75
745 | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | 766.32 | 10 | 530.42 | 13.5
746 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11565 | 556.61 | 6 | 334.11 | 95.65
747 | Murshidabad Division | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | 821.59 | 8 | 697.03 | 21.01
748 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. | SM/11231 | 150.76 | 2 | 32.08 | 0
749 | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | 478.24 | 4 | 412.17 | 0
750 | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | 623.31 | 11 | 535.63 | 23.37
751 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | 231.37 | 6 | 155.23 | 13.03
752 | Berhampur Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | 679.22 | 8 | 375.08 | 69.77
753 | Berhampur Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I | SM/14924 | 881.94 | 3 | 293.52 | 62.55
754 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14829 | 550.94 | 3 | 90.07 | 3.21
755 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | 753.28 | 8 | 383.65 | 62.46
756 | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | 739.79 | 9 | 360.43 | 53.56
757 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. | SM/14632 | 631.26 | 8 | 368.38 | 19.35
758 | Berhampur Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | 303.6 | 9 | 189.91 | 120.71
759 | Berhampur Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | 509.81 | 5 | 234.32 | 6.22
760 | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | 232.44 | 7 | 176.95 | 22.72
761 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | 546.4 | 8 | 336.32 | 24.03
762 | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | 973.05 | 8 | 807.55 | 84.07
763 | Murshidabad Division | SITARAMPUR PIPED WATER SUPPLY SCHEME. | SM/15048 | 864.73 | 8 | 485.33 | 29.4
764 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | 666.8 | 10 | 272.68 | 22.94
765 | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | 733.18 | 6 | 434.73 | 15.86
766 | Murshidabad Division | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. | SM/14945 | 941.94 | 5 | 579.59 | 3.75
767 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15061 | 807.52 | 5 | 396.44 | 2.79
768 | Berhampur Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16267 | 948.13 | 9 | 560.63 | 53.28
769 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at SURANGAPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | SM/15352 | 0 | 1 | 6.39 | 0
770 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/15267 | 888.21 | 3 | 683.07 | 0
771 | Murshidabad Division | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | 1012.65 | 6 | 815.4 | 272.72
772 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KAKRAMARI ZONE I Ground water Based PWSS, Block-Suti-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15343 | 0 | 1 | 6.39 | 0
773 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jotkamal Zone - II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15348 | 0 | 1 | 6.39 | 0
774 | Berhampur M/E Division | Implementation of affordable IoT System at Fatepur water supply Scheme in Berhampore Block, Dist- Murshidabad. | SM/15705 | 0 | 0 | 0 | 0
775 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | 687.2 | 6 | 305.91 | 0
776 | Berhampur M/E Division | Implementation of affordable IoT System at Bhandara water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15979 | 0 | 0 | 0 | 0
777 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-III, Block- Nawda, District- Murshidabad. | SM/16436 | 40.62 | 2 | 36.8 | 0
778 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16545 | 889.36 | 4 | 778.03 | 0
779 | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | 660.39 | 10 | 373.1 | 0
780 | Berhampur M/E Division | Implementation of affordable IoT System at Gobra water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15998 | 0 | 0 | 0 | 0
781 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | 579.45 | 18 | 549.68 | 222.38
782 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16497 | 40.62 | 2 | 36.81 | 0
783 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE | SM/16408 | 784.86 | 8 | 448.26 | 0
784 | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. | SM/16174 | 641.72 | 5 | 337.62 | 0
785 | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. | SM/15921 | 963.3 | 10 | 446.8 | 0
786 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-II, Block- Lalgola, District- Murshidabad. | SM/16211 | 40.62 | 2 | 36.54 | 0
787 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara | SM/08193 | 494.79 | 12 | 197.53 | 111.9
788 | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. | SM/08721 | 0 | 19 | 528.05 | 510.46
789 | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | 587.59 | 8 | 521.84 | 2.41
790 | Murshidabad Division | Augmentation of Basudevpur Zone-II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/16180 | 591.55 | 4 | 309.37 | 0.6
791 | Berhampur Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16375 | 620.94 | 7 | 396.86 | 7.73
792 | Berhampur Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16377 | 439.33 | 9 | 380.19 | 24.43
793 | Berhampur M/E Division | Implementation of affordable IoT System at Bansgara water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/16001 | 0 | 0 | 0 | 0
794 | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | 261.03 | 6 | 200.14 | 50.16
795 | Murshidabad Division | BAHARAGACHI PIPE WATER SUPPLY SCHEME. | SM/15939 | 719.97 | 5 | 340.81 | 0
796 | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | 161.21 | 8 | 167.02 | 11.55
797 | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16425 | 556.98 | 4 | 541.34 | 4.59
798 | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS | SM/16110 | 216.8 | 5 | 163.84 | 5.85
799 | Murshidabad Division | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. | SM/16169 | 832.44 | 4 | 482.58 | 0
800 | Berhampur Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS | SM/16786 | 517.85 | 6 | 261.76 | 22.52
801 | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/15726 | 763.92 | 6 | 660.01 | 0
802 | Berhampur M/E Division | Implementation of affordable IoT System at Ramnapara water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16037 | 0 | 0 | 0 | 0
803 | Berhampur M/E Division | Implementation of affordable IoT System at Harirampur water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16038 | 0 | 0 | 0 | 0
804 | Berhampur M/E Division | Implementation of affordable IoT System at Raturi ,Zone-I & II water supply Scheme in Suti-I Block, Dist- Murshidabad. | SM/15675 | 0 | 0 | 0 | 0
805 | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | 789.55 | 7 | 586.42 | 8.7
806 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | SM/16673 | 998.82 | 3 | 699.42 | 0
807 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. | SM/16674 | 996.89 | 2 | 646.82 | 0
808 | Berhampur M/E Division | Implementation of affordable IoT System at Manigram - Balarambati water supply Scheme in Sagardighi Block, Dist- Murshidabad. | SM/15702 | 0 | 0 | 0 | 0
809 | Berhampur M/E Division | Implementation of affordable IoT System at Dakshinkhanda water supply Scheme in Bharatpur-II Block, Dist- Murshidabad. | SM/15697 | 0 | 0 | 0 | 0
810 | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. | SM/17389 | 563.21 | 7 | 489.37 | 0
811 | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/18732 | 1278.27 | 9 | 1200.83 | 4.98
812 | Murshidabad Division | AOCHA AND ADJJOINING MOUJAS PWSS | SM/18470 | 1040.98 | 10 | 955.63 | 72.39
813 | Murshidabad Division | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/19016 | 826.01 | 6 | 403.16 | 6.84
814 | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B | SM/18768 | 905.71 | 50 | 813.62 | 0.34
815 | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. | SM/18465 | 1020.87 | 5 | 574.27 | 7.32
816 | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. | SM/18694 | 1333.05 | 4 | 340.38 | 0
817 | Murshidabad Division | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) | SM/18916 | 8264.61 | 2 | 7111.98 | 0
818 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba | SM/07784 | 82.98 | 2 | 82.48 | 19.86
819 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagdanga ( 314725 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV | SM/07916 | 61.03 | 1 | 41.95 | 20.67
820 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- | SM/07923 | 152.87 | 4 | 165.33 | 69.65
821 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhulauri (314671) of Dhulauri under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07673 | 142.93 | 1 | 8.8 | 0
822 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) | SM/07678 | 109.83 | 3 | 69.5 | 42.15
823 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | SM/07688 | 98.85 | 3 | 98.01 | 12.58
824 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) | SM/07690 | 129.56 | 2 | 111.5 | 38.11
825 | Berhampur Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme | SM/06985 | 99.86 | 10 | 93.7 | 50.05
826 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect | SM/08108 | 1063.3 | 9 | 886.31 | 566.02
827 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector | SM/08117 | 533.01 | 8 | 323.51 | 305.84
828 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District | SM/07200 | 57.01 | 6 | 26.14 | 45.61
829 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of | SM/07279 | 68.99 | 7 | 48.16 | 42.35
830 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Maiya Village (Code-314146) In The Command Area Of Maiya Ground Water Supply Scheme (Part-A) | SM/07734 | 215.11 | 1 | 109.18 | 109.18
831 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) | SM/07290 | 99.96 | 4 | 98.49 | 85.65
832 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part | SM/07293 | 99.3 | 5 | 112.71 | 41.62
833 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad | SM/07295 | 93.16 | 4 | 103.72 | 22.28
834 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs | SM/07509 | 97.74 | 2 | 43.58 | 2.9
835 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) | SM/07714 | 79.62 | 2 | 75.08 | 40.07
836 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Manganpara Village (Code-315662) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-A) | SM/07717 | 53.68 | 1 | 38.85 | 3.05
837 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) | SM/07722 | 43.55 | 2 | 42.89 | 6.82
838 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) | SM/07680 | 207.09 | 7 | 160.27 | 35.34
839 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I | SM/07890 | 173.44 | 2 | 128.03 | 0
840 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad | SM/07786 | 16.62 | 2 | 10.54 | 8.79
841 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba | SM/08183 | 389.91 | 18 | 377.77 | 281.76
842 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) | SM/08189 | 2032.59 | 63 | 1540.78 | 1074.92
843 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of | SM/08196 | 532.59 | 8 | 549.91 | 214.87
844 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B | SM/08202 | 873.95 | 35 | 839.01 | 381.7
845 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | 650.52 | 9 | 574.81 | 390.89
846 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water | SM/08281 | 434.98 | 10 | 296.53 | 142.07
847 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | 964.85 | 16 | 810.12 | 598.94
848 | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | 186.4 | 4 | 122.45 | 54.85
849 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under | SM/09755 | 81.3 | 2 | 34.33 | 34.33
850 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Palasi Sonadanga (314527) and Ramnapara (314496) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Bloc | SM/09756 | 87.01 | 1 | 40.79 | 40.79
851 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | 284.98 | 5 | 200.73 | 0
852 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | 36.56 | 15 | 32.84 | 23.54
853 | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Paraspur ( 314616 ) of Muradpur-Jalangi (Zone-I, Zone - II & Zone - III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block o | SM/09845 | 16.64 | 1 | 10.37 | 8.24
854 | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph | SM/10606 | 575.23 | 27 | 503.39 | 330.67
855 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | 929.25 | 9 | 564.96 | 58.78
856 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | 231.96 | 5 | 228.85 | 99.63
857 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10628 | 999.92 | 6 | 1109.85 | 551.29
858 | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | 0 | 6 | 1000.25 | 412.02
859 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | 892.32 | 10 | 784.12 | 49.97
860 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | 188.66 | 8 | 91.8 | 32.21
861 | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio | SM/11218 | 178.49 | 3 | 79.8 | 19.56
862 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I | SM/11220 | 417.3 | 2 | 341.07 | 7.54
863 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. | SM/11967 | 1295.09 | 12 | 595.53 | 58.29
864 | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | 369.94 | 8 | 310.67 | 97.73
865 | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | 902.45 | 9 | 478.12 | 213.25
866 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl | SM/08277 | 418.69 | 4 | 122.39 | 101.55
867 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13927 | 758.89 | 10 | 500.91 | 25.73
868 | Berhampur Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | 797.62 | 8 | 405.95 | 156.84
869 | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | 938.24 | 8 | 754.84 | 19.86
870 | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | 597.39 | 7 | 562.69 | 0
871 | Berhampur Division I | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/14426 | 501.29 | 7 | 213.93 | 20.36
872 | Murshidabad Division | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | 271.8 | 5 | 203.06 | 0
873 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | 686.91 | 8 | 307.57 | 49.11
874 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | 613 | 9 | 278.22 | 101.74
875 | Berhampur Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | 662.31 | 12 | 432.18 | 52.3
876 | Berhampur Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14921 | 989.95 | 9 | 673.33 | 239.97
877 | Berhampur Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. | SM/14922 | 855.81 | 9 | 564.14 | 89.42
878 | Berhampur Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14923 | 775.12 | 11 | 512.41 | 15.24
879 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at GODHANPARA PWSS (ZONE- I ) Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15291 | 0 | 1 | 6.39 | 0
880 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dakshin Sekhhalipur Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15292 | 0 | 1 | 6.39 | 0
881 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bachhara Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15295 | 0 | 1 | 6.38 | 0
882 | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | 548.31 | 9 | 303.25 | 35.18
883 | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/15070 | 847.95 | 7 | 665.87 | 66.11
884 | Murshidabad Division | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | 790.62 | 5 | 647.94 | 4.91
885 | Berhampur Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14920 | 933.72 | 11 | 592.77 | 35.37
886 | Murshidabad Division | MARURA AND ADJOINING MOUJAS PWSS | SM/14235 | 1168.32 | 4 | 933.02 | 0
887 | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | 1141.76 | 7 | 958.59 | 247.19
888 | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. | SM/16246 | 855.97 | 9 | 493.3 | 0
889 | Murshidabad Division | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. | SM/16247 | 541.38 | 3 | 524.74 | 0
890 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16265 | 429.02 | 4 | 34.01 | 0
891 | Murshidabad Division | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | 702.59 | 5 | 540.44 | 38.01
892 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bahadurpur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. | SM/15341 | 0 | 1 | 6.39 | 0
893 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at NABIPUR Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15346 | 0 | 1 | 6.39 | 0
894 | Berhampur M/E Division | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Kasiadanga Zone- I & II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | SM/15349 | 0 | 1 | 6.39 | 0
895 | Murshidabad Division | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. | SM/16240 | 541.38 | 4 | 523.25 | 8.83
896 | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of | SM/07676 | 150.4 | 4 | 109.63 | 52.6
897 | Berhampur Division I | Mini piped water supply scheme (maximum 100 households) Village-Arazi Saikuli, Block-Murshidabad -Jiaganj, District- Murshidabad. | SM/16431 | 38.81 | 2 | 35.28 | 0
898 | Berhampur Division I | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. | SM/16433 | 31.51 | 2 | 28.81 | 0
899 | Berhampur M/E Division | Implementation of affordable IoT System at Faridpur water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16004 | 0 | 0 | 0 | 0
900 | Berhampur Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS | SM/16015 | 803.16 | 5 | 440.18 | 9.55
901 | Berhampur M/E Division | Implementation of affordable IoT System at Paschimrampur water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15977 | 0 | 0 | 0 | 0
902 | Berhampur Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. | SM/16437 | 40.62 | 2 | 36.8 | 0
903 | Murshidabad Division | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | 81.23 | 4 | 73.66 | 0
904 | Berhampur M/E Division | Implementation of affordable IoT System at Lalgola water supply Scheme in Lalgola Block, Dist- Murshidabad. | SM/15986 | 0 | 0 | 0 | 0
905 | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | 590.51 | 5 | 488.49 | 2.67
906 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Alighata, Block- Lalgola, District- Murshidabad. | SM/16496 | 40.62 | 2 | 36.81 | 0
907 | Berhampur Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-II, Block- Nawda, District- Murshidabad. | SM/16498 | 40.62 | 2 | 36.79 | 0
908 | Berhampur Division I | Mini piped water supply scheme (maximum 100 households) Village-Sibnagar Zone-V, Block-Nawda, District- Murshidabad. | SM/16501 | 33.09 | 2 | 30.23 | 0
909 | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | 503.35 | 8 | 174.12 | 53.86
910 | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | 800.01 | 7 | 764.55 | 15.75
911 | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. | SM/16179 | 898.14 | 11 | 646.79 | 0
912 | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16274 | 932.74 | 4 | 754.79 | 81.83
913 | Murshidabad Division | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | 81.23 | 4 | 73.72 | 0
914 | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | 466.43 | 6 | 413.88 | 2.97
915 | Berhampur M/E Division | Implementation of affordable IoT System at Sundarpur water supply Scheme in Bhagwangola-I Block, Dist- Murshidabad. | SM/15984 | 0 | 0 | 0 | 0
916 | Murshidabad Division | CHANDAMARI PIPED WATER SUPPLY SCHEME. | SM/16218 | 520.98 | 6 | 474.79 | 2.15
917 | Murshidabad Division | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | 367.21 | 6 | 292.89 | 4.27
918 | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16556 | 221.25 | 3 | 158.8 | 0
919 | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | 275.73 | 4 | 159.31 | 15.34
920 | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. | SM/15945 | 824.91 | 14 | 552.4 | 0
921 | Berhampur M/E Division | Implementation of affordable IoT System at Simulia- Jaulia water supply Scheme in Bharatpur-II Block, Dist- Murshidabad. | SM/15739 | 0 | 0 | 0 | 0
922 | Berhampur M/E Division | Implementation of affordable IoT System at Benipur water supply Scheme in Bhagwangola-II Block, Dist- Murshidabad. | SM/16012 | 0 | 0 | 0 | 0
923 | Berhampur M/E Division | Implementation of affordable IoT System at Mahesail water supply Scheme in Suti-II Block, Dist- Murshidabad. | SM/15679 | 0 | 0 | 0 | 0
924 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15746 | 975.16 | 7 | 723.22 | 90.03
925 | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | 198.62 | 6 | 124.06 | 4.24
926 | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | 460.95 | 7 | 431.3 | 53.36
927 | Murshidabad Division | BERBARI AND ADJOINING MOUJAS PWSS | SM/15694 | 146.43 | 4 | 105.14 | 8.12
928 | Berhampur M/E Division | Implementation of affordable IoT System at Giria Kismat water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15715 | 0 | 0 | 0 | 0
929 | Berhampur M/E Division | Implementation of affordable IoT System at Jotkamal Zone-I &II water supply Scheme in Raghunathganj-II Block, Dist- Murshidabad. | SM/15721 | 0 | 0 | 0 | 0
930 | Berhampur M/E Division | Implementation of affordable IoT System at Kagram water supply Scheme in Bharatpur-II Block, Dist- Murshidabad. | SM/15699 | 0 | 0 | 0 | 0
931 | Berhampur Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | 1325.56 | 28 | 1225.51 | 666.05
932 | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. | SM/15749 | 999.15 | 11 | 1128.32 | 62.56
933 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16672 | 998.65 | 2 | 698.74 | 0
934 | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | 479.79 | 10 | 368.19 | 1.65
935 | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | 959.64 | 11 | 689.18 | 39.08
936 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16985 | 965.79 | 2 | 634.73 | 0
937 | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IV)to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . | SM/16987 | 950.83 | 1 | 608.95 | 0
938 | Berhampur M/E Division | Implementation of affordable IoT System at Sagardighi, water supply Scheme in Sagardighi Block, Dist- Murshidabad. | SM/15707 | 0 | 0 | 0 | 0
939 | Murshidabad Division | BHATPARA AND ADJOINING MOUJAS | SM/18430 | 1170.19 | 3 | 1034.8 | 0
940 | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. | SM/18774 | 1593.91 | 7 | 945.75 | 4.85
941 | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. | SM/19121 | 1667.04 | 7 | 828.71 | 5.22
942 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. | SM/19122 | 1550.75 | 5 | 704.51 | 0
943 | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | 1218.84 | 6 | 909.39 | 90.69
944 | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. | SM/18516 | 1348.64 | 8 | 752.99 | 1.78
945 | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. | SM/18832 | 2107.4 | 13 | 1187.12 | 13
946 | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. | SM/18665 | 2200.3 | 7 | 1711.17 | 23.97
947 | Berhampur Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | 1308.69 | 8 | 936.71 | 165.28
948 | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/18444 | 1407.24 | 14 | 769.51 | 13.52
949 | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. | SM/18705 | 1703.43 | 11 | 910.86 | 86.81
950 | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. | SM/13044 | 0 | 71 | 122.09 | 104.95
951 | Berhampur Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. | SM/16268 | 0 | 9 | 25.94 | 18.94
952 | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & data uploding charges related to water Quality Monitoring & Surveillance Activities Under Jal Jeevan Mission . | SM/19077 | 0 | 0 | 0 | 0
953 | Resources Division | On-site assessment with sample collection & testing of AIRPs, CWPPs installed in Murshidabad district including supply & delivery of 3 Nos. On-site Mobile Analysis System with 10644 consumables in addition to monitoring & processing data of AIRPs & CWPPs | null | 0 | 0 | 0 | 0
954 | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. | SM/06630 | 0 | 28 | 136.66 | 89.51
955 | Murshidabad Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Murshidabad District Under Murshidabad Division (16 nos) Block | SM/09856 | 0 | 0 | 0 | 133.36
956 | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | 0 | 8 | 47.58 | 42.28
957 | Murshidabad Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERD RURAL AREA OF MURSHIDABAD DISTRICT IN WEST BENGAL | SM/14638 | 0 | 0 | 0 | 609.23
958 | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. | SM/15310 | 0 | 14 | 29.3 | 10.77
959 | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. | SM/19076 | 0 | 105 | 316.94 | 73.56
960 | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid | SM/08685 | 0 | 4 | 21.01 | 14.78
961 | Berhampur M/E Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Executive Engineer, Mechanical/Electrical Division Berhampore, PHE Dte. | SM/17192 | 0 | 2 | 6.41 | 5.26
962 | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. | SM/18195 | 0 | 5 | 276.68 | 264.86
963 | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . | SM/18272 | 0 | 11 | 211.97 | 9.89
964 | Murshidabad Division | Operational Charges Of Drinking Water Testing Laboratories related to Water Quality Monitoring & Surveillance Activities under JJM of Different Water Testing Laboratories under Murshidabad Division P.H.E. Dte. | SM/19260 | 0 | 0 | 0 | 0
965 | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | 0 | 22 | 179.33 | 101.16
Total |  |  |  | 549296.15 | 0 | 398471.13 | 61881.65