## Work Order Tracking (Rs. in Lak
Work Order Tracking (Rs. in Lakh)
SL. No. | Division | Scheme | Scheme Sm Code | Sanctioned Cost | No. of Work Orders | Work Value | Payment
1 | RCFA Division I | Retrofitting of Gourbazar PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09063 | 29.57 | 6 | 30.48 | 23.87
2 | RCFA Division I | AUGMENTATION OF ITAPARA PIPED WATER SUPPLY SCHEME | SM/10844 | 945.42 | 17 | 732.9 | 83.48
3 | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) | SM/10212 | 663.97 | 27 | 796.05 | 560.81
4 | RCFA Division I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | 774.12 | 28 | 775.97 | 452.35
5 | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME | SM/10999 | 57.63 | 2 | 45.57 | 18.19
6 | RCFA Division I | Augmentation of Ondal (Phase-I) Water Supply Scheme | SM/10641 | 887.89 | 18 | 795.48 | 480.62
7 | RCFA Division I | Retrofitting of 4 Nos. PWSS for providing FHTC within Raniganj, Andal, Salanpur, Pandabeswar of Paschim Bardhaman district | SM/07392 | 627.42 | 72 | 647.42 | 609.36
8 | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | 1310.24 | 54 | 1295.26 | 789.72
9 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | 579.22 | 19 | 568.78 | 219.71
10 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | 831.03 | 9 | 814.99 | 573.41
11 | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/11932 | 657.52 | 9 | 598.63 | 548.32
12 | RCFA Division I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-B) | SM/09060 | 244.75 | 24 | 266.01 | 237.45
13 | RCFA Division I | Retrofitting of Roshna PWSS for providing FHTC within Barabani Block of Paschim Bardhaman District under RCFA Division-I. | SM/09062 | 82.87 | 9 | 99.61 | 79.24
14 | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | SM/11937 | 529.96 | 10 | 508.99 | 430.24
15 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16900 | 98.83 | 3 | 111.07 | 49.81
16 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16902 | 94.57 | 4 | 81.28 | 37.47
17 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA | SM/15657 | 929.97 | 15 | 843.09 | 355.38
18 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18888 | 175.3 | 4 | 55.01 | 0.55
19 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18826 | 460.11 | 6 | 351.81 | 180.68
20 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18877 | 313.27 | 6 | 259.75 | 83.6
21 | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | SM/18417 | 2340.61 | 21 | 2234.9 | 458.79
22 | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | 86.82 | 25 | 140.17 | 52.88
23 | RCFA Division I | Retrofitting of Chotkara Kanskuli PWSS (Zone-IV) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07561 | 94.68 | 11 | 89.84 | 86.53
24 | RCFA Division I | Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block of Paschim Bardhaman District under RCFA Division-I. | SM/09061 | 48.52 | 4 | 24.94 | 17.54
25 | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | 188.03 | 20 | 231.19 | 161.34
26 | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | 1167.42 | 35 | 1236.9 | 1030.22
27 | Asansol Mechanical Division | Augmentation work for providing House to House Connection from existing distribution system for Nuni and Adjoining Mouzas and Panchgachi Zone Piped Water Supply Scheme . | SM/10144 | 25.6 | 9 | 26.31 | 22.08
28 | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | SM/11224 | 633.08 | 7 | 594.25 | 525.02
29 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | 896.96 | 11 | 925.96 | 253.11
30 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-19) UNDER RCFA DIVISION-I PHE DTE. | SM/12216 | 868.69 | 10 | 855.96 | 380.51
31 | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) | SM/13862 | 33.6 | 2 | 33.59 | 0
32 | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | SM/16249 | 579.21 | 27 | 552.69 | 268.92
33 | Asansol Mechanical Division | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site under RCFA-III (Zone-I) Water Supply Scheme, Block:- Faridpur-Durgapur, Dist:- Paschim Bardhaman. | SM/16775 | 198.21 | 4 | 192.39 | 80.54
34 | RCFA Division I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | 988.24 | 15 | 945.95 | 324.53
35 | Durgapur W/S Division | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18887 | 220.53 | 4 | 65.97 | 2.77
36 | RCFA Division I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | 5020.98 | 89 | 3951.5 | 1420.8
37 | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | 96.32 | 17 | 106.6 | 89.4
38 | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | 943.11 | 43 | 912.21 | 676.33
39 | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | SM/10311 | 389.8 | 15 | 439.97 | 316.2
40 | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | 811.61 | 31 | 785.07 | 682.38
41 | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | SM/12726 | 2832.34 | 69 | 2817.3 | 1381.16
42 | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | SM/11933 | 275.4 | 7 | 238.83 | 135.68
43 | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | 1841 | 150 | 2953.42 | 1801.09
44 | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Maheshpur,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-A) | SM/13879 | 42.44 | 1 | 37.9 | 0
45 | RCFA Division I | Retrofitting of Chotkara Kanskuli PWSS (Zone-III) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07560 | 94.68 | 7 | 90.19 | 89.69
46 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15663 | 227.43 | 7 | 183.29 | 71.13
47 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | 543.54 | 15 | 528.77 | 210.19
48 | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | SM/11282 | 254.22 | 9 | 235.25 | 180.26
49 | RCFA Division I | AUGMENTATION OF PANURIA PIPED WATER SUPPLY SCHEME | SM/10165 | 971.48 | 23 | 987.47 | 603.26
50 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone-2A) Block - Andal, Dist - Paschim Bardhaman | SM/12226 | 440.82 | 9 | 408.59 | 113.64
51 | RCFA Division I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | 997.15 | 18 | 994.1 | 542.83
52 | RCFA Division I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | 904.57 | 18 | 903.17 | 420.19
53 | Durgapur W/S Division | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) | SM/13863 | 34.64 | 1 | 34.64 | 1.46
54 | Durgapur W/S Division | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | SM/13866 | 47.8 | 1 | 47.8 | 20.74
55 | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16250 | 638.71 | 13 | 425.69 | 233.18
56 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15639 | 989.75 | 9 | 643.2 | 418.72
57 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16903 | 64.9 | 4 | 60.39 | 7.09
58 | RCFA Division I | Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block. | SM/09065 | 92.6 | 16 | 77.78 | 66.29
59 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18467 | 1401.03 | 19 | 1031.89 | 385.01
60 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18469 | 2403.3 | 35 | 1600 | 299.92
61 | RCFA Division I | Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block. | SM/09064 | 169.66 | 6 | 136.76 | 133.14
62 | RCFA Division I | WATER SUPPLY CONNECTION TO SCHOOL(419) AND ANGANWARI(1281) THROUGH RETROFITTING FROM EXISTING AND ONGOING PIPED WATER SUPPLY SCHEMES UNDER RCFA DIVISION-I, P.H.E DTE. | SM/10287 | 0 | 30 | 176.65 | 102.57
63 | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10210 | 780.77 | 35 | 872.24 | 685.89
64 | RCFA Division I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | 866.51 | 12 | 715.42 | 88.07
65 | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | SM/11228 | 309.98 | 9 | 292.52 | 232.55
66 | Durgapur W/S Division | BANAGRAM PIPED WATER SUPPLY SCHEME | SM/11223 | 34.78 | 2 | 24.49 | 18.75
67 | RCFA Division I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | 754.7 | 14 | 960.08 | 469
68 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | 462 | 5 | 459.98 | 88.31
69 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | SM/12225 | 424.86 | 6 | 409.95 | 118.29
70 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | 809.92 | 10 | 823.83 | 352.52
71 | RCFA Division I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE | SM/12024 | 365.56 | 3 | 341.62 | 340.1
72 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | 901.05 | 10 | 909.35 | 318.41
73 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-17) UNDER RCFA DIVISION-I PHE DTE. | SM/12218 | 878.95 | 21 | 853.3 | 370.15
74 | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | SM/13685 | 137.13 | 12 | 139.52 | 58.91
75 | Durgapur W/S Division | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) | SM/13861 | 41.75 | 1 | 41.75 | 0
76 | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) | SM/13864 | 40.28 | 1 | 40.28 | 0
77 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/16901 | 340.79 | 4 | 297.89 | 90.01
78 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/15659 | 157.71 | 4 | 118.24 | 58.39
79 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JEMUA, UNDER DURGAPUR W/S DIVISION , BLOCK : DURGAPUR FARIDPUR, DISTRICT : PASCHIM BARDDHAMAN | SM/18890 | 219.38 | 5 | 182.55 | 69.57
80 | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR DAKHIN KHANDA MOUZA (Jl No. 36) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09389 | 111 | 16 | 116.55 | 103.04
81 | RCFA Division I | Retrofitting of PWSS for Ukhra & adj areas for providing FHTC within Ondal & Pandabeswar Block (Part-A) | SM/09059 | 244.75 | 29 | 236.55 | 236.11
82 | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) | SM/10208 | 700.46 | 48 | 757.81 | 629.43
83 | RCFA Division I | Augmentation of Madantor Water Supply Scheme | SM/10845 | 587.44 | 16 | 572.33 | 204.19
84 | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | SM/10998 | 41.17 | 2 | 26.92 | 20.58
85 | RCFA Division I | Augmentation of Roshna Piped Water Supply Scheme . | SM/10642 | 844.67 | 32 | 801.65 | 505.68
86 | RCFA Division I | Improvement of RCFA (Part-I) Piped Water Supply Scheme. | SM/09916 | 11874.12 | 165 | 10425.28 | 8763.81
87 | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | 773.34 | 8 | 771.39 | 533.85
88 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | 530.12 | 16 | 533.05 | 218.9
89 | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07519 | 97.53 | 21 | 95.99 | 64.88
90 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | 481.52 | 9 | 411.88 | 171.65
91 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | 568.7 | 9 | 468.25 | 272.94
92 | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | SM/15666 | 905.76 | 18 | 888.76 | 328.39
93 | Asansol Mechanical Division | Providing and Installation of Sub-Station equipments and other accessories ar Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block: Raniganj, Dist: Paschim Bardhaman. | SM/16777 | 204.12 | 3 | 203.34 | 84.97
94 | Asansol Mechanical Division | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head WOrks site under RCFA Part-III (Zone-II) Water Supply Scheme, Block:- Pandabeshwar, Dist:- Paschim Bardhaman. | SM/18889 | 250.38 | 2 | 145.06 | 0.03
95 | Durgapur W/S Division | Ground water based mini piped water supply scheme (Max 100 House Hold) for Pathardiha,GP-Gopalpur,Block -Kanksa,Dist-Paschim Bardhaman under Durgapur W/s Division,PHE Dte (Part-G) | SM/18745 | 39.36 | 1 | 39.36 | 12.25
96 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18825 | 306.19 | 5 | 238.66 | 41.66
97 | RCFA Division I | Retrofitting of Chotkara Kanskuli PWSS (Zone-II) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07559 | 94.74 | 6 | 111.5 | 89.68
98 | RCFA Division I | Retrofitting of Improvement of Babani Zone PWSS for Providing FHTC Within Barabani Block of Paschim Bardhaman District | SM/07562 | 62.01 | 3 | 63.09 | 58.95
99 | RCFA Division I | RETROFITTING OF BAHULA MOUZA UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN PANDABESWAR BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09388 | 220.61 | 27 | 252.52 | 189.82
100 | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | SM/09242 | 0 | 7 | 10.72 | 10.08
101 | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | 489.84 | 31 | 390.39 | 416.81
102 | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman | SM/10372 | 0 | 43 | 945.55 | 803.49
103 | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME | SM/10996 | 54.17 | 1 | 8.7 | 34.43
104 | RCFA Division I | AUGMENTATION OF SARSHATALI PIPED WATER SUPPLY SCHEME | SM/10605 | 608.44 | 18 | 579.13 | 275.03
105 | RCFA Division I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | 996.67 | 13 | 1000.59 | 470.75
106 | RCFA Division I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | 808.08 | 14 | 703.8 | 332.79
107 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | 771.55 | 19 | 837.86 | 304.63
108 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | 731.25 | 18 | 702.78 | 284.56
109 | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. | SM/11934 | 51.33 | 2 | 44.26 | 25.67
110 | RCFA Division I | Sub-surface Water Based Water Supply Scheme for Bagdiha and its adjoining areas to Accommodate FHTC in Jamuria Block, District - Paschim Bardhaman | SM/13416 | 909.45 | 24 | 839.35 | 267.73
111 | RCFA Division I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | 941.12 | 28 | 438.45 | 82.89
112 | RCFA Division I | Retrofitting of Chotkara Kanskuli PWSS (Zone-I) for Providing FHTC Within Salanpur & Barabani Block of Paschim Bardhaman District | SM/07558 | 94.74 | 8 | 91.04 | 91.04
113 | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman | SM/10373 | 0 | 38 | 395.58 | 371.2
114 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | 610.16 | 24 | 609.09 | 405.77
115 | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | SM/11454 | 2799.63 | 45 | 2675.76 | 1672.05
116 | RCFA Division I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | 661.28 | 17 | 625.74 | 391.39
117 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | 681.87 | 18 | 732.4 | 337.86
118 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | 833.27 | 17 | 759.9 | 449.86
119 | RCFA Division I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | 689.44 | 16 | 679.3 | 200.58
120 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | 818.76 | 13 | 836.22 | 266.98
121 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12A) UNDER RCFA DIVISION-I PHE DTE. | SM/12030 | 991.93 | 7 | 1016.31 | 481.6
122 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | 587.31 | 9 | 566.55 | 85.26
123 | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | 910.23 | 12 | 900.15 | 314.22
124 | RCFA Division I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | 898.82 | 37 | 863.16 | 528.92
125 | RCFA Division I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | 882.66 | 11 | 797.81 | 405.33
126 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18886 | 350.95 | 6 | 283.23 | 66.42
127 | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | SM/18824 | 860 | 7 | 583.61 | 182.84
128 | RCFA Division I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | SM/18769 | 46405.37 | 54 | 44403.75 | 7243.58
129 | RCFA Division I | Supply and delivery of Chemicals, Consumables, Glassware, etc. required for smooth running. | SM/06618 | 0 | 0 | 0 | 0
130 | RCFA Division I | Operational Charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. | SM/19257 | 0 | 0 | 0 | 0
131 | RCFA Division I | Supply, Delivery and Installation of Desktop Computers and Other Allied Accessories (Through GeM Portal) for Gopalpur Camp Office under RCFA Division-I PHE Dte. | null | 0 | 0 | 0 | 0
132 | Asansol Mechanical Division | Procurement of Chemical & Consumables, Glassware etc. required for smooth running of Laboratory at Kalyaneswari Water treatment Plant. | SM/06635 | 0 | 0 | 0 | 6.84
133 | RCFA Division I | Supply delivery and installation of desktop computers and other allied accessories (through GeM portal) under RCFA Division-I PHE Dte. | SM/10680 | 0 | 5 | 9.74 | 9.74
134 | RCFA Division I | Orientation and Mass Awareness Generation (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Paschim Bardhaman | null | 0 | 0 | 0 | 0
135 | Asansol Mechanical Division | Procurement of Computer and Peripherals for the office use in Asansol Mechanical Division, Kalyaneswari Water Testing Laboratory, P.H.E. Dte., District:- Paschim Bardhaman. | SM/17412 | 0 | 2 | 5.75 | 5.75
136 | RCFA Division I | Providing service by assigning resource person for a period of 3 month supervision of process of preparation for NABL recognition for chemical testing of potable water of sub-District level water quality testing laboratory including supply, installation o | SM/16428 | 0 | 3 | 4.75 | 2.38
137 | RCFA Division I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman | SM/13358 | 0 | 3 | 5.44 | 3.08
138 | Asansol Mechanical Division | Operational charges of PHED Managed Laboratory under Asansol Mechanical Division Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17190 | 0 | 0 | 0 | 0
139 | Durgapur W/S Division | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. | SM/06638 | 0 | 2 | 7.55 | 2.46
140 | RCFA Division I | DRINKING WATER SAMPLES COLLECTION, TESTING OF DRINKING WATER SAMPLES THROUGH FTK & UPLOADING CHARGES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JJM FROM FEB 22 TO MAR 23 | SM/11817 | 0 | 2 | 59.12 | 13
141 | Durgapur W/S Division | Operation charges of 2 Two) Nos Sub-District Laboratories under Durgapur Water Supply Division,PHE Dte ,Dist-Paschim Bardhaman related to Water quality monitoring and surveillance programme under Jal jeevan Mission. | SM/13908 | 0 | 1 | 1.09 | 0
142 | RCFA Division I | Supply, delivery and installation of Desktop computers and other allied accessories (through GeM portal) under Central Circle, PHE Directorate. | SM/13406 | 0 | 9 | 7.41 | 1.96
143 | Asansol Mechanical Division | Operational Charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/19258 | 0 | 0 | 0 | 0
144 | RCFA Division I | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Paschim Barddhaman District. | SM/08984 | 0 | 1 | 0.68 | 168.37
Total |  |  |  | 133095.55 | 0 | 126703.25 | 52788.46